## Sheet1
Rank	Who	Target	ID	Sev	Pri	Summary
2	METABUG	.............	404403	maj	Hig	Firefox Metabug
4	Joanie	GNOME 2.19.5	407941	maj	Nor	Infer labels for objects in HTML content
5	Joanie	TBS	407663	nor	Nor	[blocked] Support the "Find" operation in Firefox better
8	Willie	GNOME 2.19.2	412677	maj	Nor	[blocked] Navigation to links with { overflow:hidden } stylesheet results in bad behavior
9	Willie	GNOME 2.19.2	423435	nor	Nor	Orca is too chatty when loading a page in Firefox
10		TBS	414762	nor	Nor	[blocked] Control Home/End, Up/Down Arrow don't always work in Firefox
11	Joanie	GNOME 2.19.4	423427	nor	Nor	Need to add form field structural navigation in Firefox
12	Willie	GNOME 2.19.90	423348	nor	Nor	Support DHTML, AJAX, ARIA in Firefox/Gecko
13	Joanie	TBS	428025	nor	Nor	[pending] Links should not be spoken twice when down arrowing in firefox
14	Joanie	TBS	414657	enh	Nor	Linked headings should be announced as both heading and link
15		TBS	433951	nor	Nor	Making changes in the Orca Preferences dialog resets the caretContext in Firefox
16	Willie	TBS	414738	nor	Nor	Flat review in Firefox doesn't start at caret position
18	Willie & Joanie	TBS	412661	enh	Nor	Gecko.py: determine isUselessObject vs. isLayoutOnly relationship
19		TBS	415812	nor	Nor	[blocked] Orca sometimes provides incorrect information regarding table headers
20		TBS	420540	enh	Nor	Firefox keyboard control wish list.
21		TBS	433655	enh	Nor	Orca's structural navigation should wrap at the end of a page
22		TBS	419135	nor	Nor	[blocked] Tables with column headers have accessibility issues
23	Lynn	TBS	420324	nor	Nor	Problems building Access Bridge v1.5.0
24	Rich	GNOME 2.19.90	400716	enh	Nor	[pending] sayAll should be done by sentences.
25	Willie	GNOME 2.19.1	412200	maj	Nor	Orca L10N / Translation issues
26	Lynn	GNOME 2.19.1	412837	nor	Nor	Orca needs test code coverage reporting
27	Lynn	GNOME 2.19.1	415061	maj	Nor	regression test results should be repeatable
28	Lynn	TBS	416332	nor	Nor	Orca test coverage needs to be extended
28.5	Lynn	TBS	435623	nor	Nor	Java Platform Metabug
30	Rich	GNOME 2.20!	354479	nor	Nor	[blocked] [requirement] Automatic presentation of "balloon" type messages
32	METABUG	.............	404411	nor	Nor	OpenOffice Metabug
35	Rich	GNOME 2.20!	356066	min	Nor	[blocked] Items in OOo's Navigator window are not always spoken
36	Rich	GNOME 2.20!	356060	enh	Nor	[blocked] Provide access to tree item level and state in OOo Navigator
37	Rich	TBS	413909	nor	Nor	[blocked] Orca can no longer provide "smarts" for spell checking in OOo Writer v2.1 (or later)
38	Rich	GNOME 2.20!	363827	enh	Nor	[blocked] Insert F should provide access to the style and font name in OOo Writer
39	Mike Spec	GNOME 2.20!	372965	enh	Nor	[blocked] Insert F should provide access to ALL attributes applied to text in OOo Writer
40	Joanie	GNOME 2.20!	363830	enh	Nor	[blocked] Provide feedback in OOo when toggling bold, underline, and italics
41	Rich	GNOME 2.20!	404046	enh	Nor	[blocked] Provide feedback in OOo when a command changes attributes
42	Rich	GNOME 2.20!	376517	nor	Nor	[blocked] Orca does not report indentation in OOo Writer documents correctly
43	Rich	GNOME 2.20!	361737	maj	Nor	[blocked] It is not possible to navigate to form controls using the keyboard in OOo Writer
44	Rich	TBS	433401	nor	Nor	"Frozen" cells seems to interfere with setting dynamic headers in Calc
45	Rich	TBS	412252	nor	Nor	[blocked] OOo Writer crash when using Orca
47	Rich	TBS	429390	nor	Nor	Braille stays on current line after pressing return at end of line in OOo Writer
48	Rich	TBS	426010	enh	Nor	Implement verbalized links in OOo
49		GNOME 2.20?	364772	nor	Nor	[blocked] Orca can not detect miss-spelled words on the fly in Openoffice
50		TBS	431030	maj	Nor	[blocked] Cannot use keyboard to navigate gnome-panel notification area
51	Mike	GNOME 2.20!	382601	enh	Nor	Orca should indicate selected text on the braille display
52	Wilie	TBS	434600	nor	Nor	cursor routing problem in gedit
53	Mike Spec	GNOME 2.20!	400720	enh	Nor	[requirement] Support accurate presentation of text attributes on the braille display
54		TBS	419139	nor	Nor	[blocked] Gnome Screen saver password dialog not accessible
55	Rich	GNOME 2.20?	354466	nor	Nor	[requirement] Watched Objects
56	Rich	GNOME 2.20?	354468	min	Nor	[requirement] Bookmarked Objects
57		TBS	430402	nor	Nor	[blocked] Orca unable to speak last character of each "sentence" when doing a sayAll in OOo Writer
58		TBS	423323	cri	Nor	[blocked] Thunderbird 3.0-a1 crashes every time I close a message.
59	METABUG	.............	423346	nor	Nor	Evolution Metabug
60		TBS	349978	nor	Nor	[blocked] Orca does not announce a message change when deleting a message in evolution
61		TBS	353470	nor	Nor	[blocked] Orca does not speak when the last message in the Evolution mail message header summary list is deleted.
62		TBS	353458	nor	Nor	[pending] Text selection in Evolution "New Message" text area is not reported.
63		TBS	422487	enh	Nor	[blocked] Ability to jump to the start of the message in Evolution.
64		TBS	424149	nor	Nor	Evolution mail message window inconsistent with item selected in mail header list.
65		TBS	353434	nor	Nor	[blocked] Backspaced characters in the 'subject' and 'to' lines of evolution are not announced.
66		TBS	401889	nor	Nor	[blocked] Orca does not speak backspaced characters in certain dialogs
67		TBS	418287	nor	Nor	[blocked] Treat words separated by non-breaking spaces as a single word in OOo
68	Willie	TBS	419742	enh	Nor	Add it the ability to switch languages.
69	Rich	GNOME 2.20?	364518	enh	Nor	Create a GUI interface to the pronunciation dictionary.
70	Joanie	GNOME 2.20?	425563	enh	Nor	[blocked] Provide structural navigation of PDF documents
71		TBS	423436	nor	Nor	RealPlayer doesn't seem to work well with Orca
72		TBS	407658	nor	Nor	[blocked] Cannot access status bar information in Gedit
73	Willie	TBS	405759	enh	Nor	Distinguish Q and BLOCKQUOTE in (X)HTML content
74	Willie	GNOME 2.20!	345399	nor	Nor	Key echo missing alpha numeric and punctuation keys.
75		TBS	402835	nor	Nor	[blocked] In Firefox 3.0 a submenu of the bookmarks menu cannot be accessed, if speech is activated.
76	Rich	TBS	422475	enh	Nor	Orca should speak the word deleted if You enter Control-Backspace.
77	METABUG	.............	404409	nor	Hig	Thunderbird Metabug
78	Willie/Rich	TBS	409728	nor	Nor	Orca repeats mouse-selected text numerous times in thunderbird
79	Rich	TBS	409736	enh	Nor	[blocked] Orca does not announce the beginning of strings pasted into thunderbird
80		TBS	374537	nor	Nor	[blocked] Thunderbird 3.0 checkbox table cells in subscribe dialog do not provide checked/unchecked state
81		TBS	433323	nor	Nor	Orca does not show the tabs list in Firefox 3.
82		TBS	362627	nor	Nor	[blocked] Thunderbird folder properties: no relationship between page tabs and page contents
83		TBS	381455	nor	Nor	[blocked] Thunderbird does not present labels around dialog text entries
84		TBS	373135	nor	Nor	[blocked] Thunderbird 3.0 add-on dialog buttons not spoken
85	Rich	TBS	432308	nor	Nor	[blocked] Problem with Evolution and threads always speaking "expanded 0 items".
86		GNOME 2.18!	354467	maj	Hig	Opening URL in Freeloader hangs Orca
87	Willie	GNOME 2.20!	NO ID	maj	Hig	Accessible Installation of Solaris Express
88	Joanie	TBS	412100	nor	Nor	Text selection in Firefox fails when Orca controls the caret
89	Willie	GNOME 2.20!	404422	nor	Nor	Support per-URL Scripts
90	Willie	TBS	419123	nor	Nor	Modified speech settings do not change immediately in preferences dialog
91	Lynn	TBS	410088	nor	Nor	NetworkManager applet not spoken when network is disconnected
92		GNOME 2.20!	352163	nor	Nor	[blocked] Orca announces incorrect info in Deskbar Applet
93	Rich	TBS	409731	enh	Nor	Orca should speak text selected by the mouse
94		TBS	434564	enh	Nor	A wish for flat review to be able to move in smallish increments
95	Willie	TBS	375782	nor	Nor	The performance of orca full screen magnification is not good.
96	Willie	TBS	375396	nor	Nor	Orca failed to exit after stopping the full screen mag.
97	Willie	TBS	399639	cri	Nor	Orca crashes and magnifier hangs if user enables the magnifier.
98	Willie	TBS	403760	nor	Nor	Emacspeak speech factory doesn't always shutdown/restart correctly
99	Willie	TBS	355525	maj	Nor	Orca skipped one line of web content in flatreview mode.
100		GNOME 2.20!	383120	nor	Nor	[blocked] Ekiga conversation message cannot be read by orca
101		GNOME 2.20!	354782	nor	Nor	[blocked] gnome-system-monitor "Resources" tab is inaccessible
102		GNOME 2.20!	356041	nor	Nor	Previous link in desktop helper can not be read by orca.
103		GNOME 2.20!	356042	nor	Nor	[blocked] The labels in File Management Preferences (nautilus-file-management-properties) window were not reported by orca.
104		GNOME 2.20!	397680	nor	Nor	[blocked] OOo Writer Save As Encoded Text throws up a dialog that is not properly spoken
105		GNOME 2.20!	385828	nor	Nor	[blocked] Can not use agenda wizard in OpenOffice.org
106		GNOME 2.20!	357545	nor	Nor	[blocked] Orca does not speak all buttons in openoffice database table creation wizzard
108	Willie	GNOME 2.20?	400717	enh	Nor	Orca should support multi-lingual text.
109	Willie	TBS	397306	enh	Nor	Orca's default synthesis engine choice should take language into account
110	Mike/Joanie Spec	GNOME 2.20	400728	nor	Nor	[requirement] Orca should provide a means to quickly set often-used preferences
111		TBS	347691	nor	Nor	[blocked] In standard print dialog, printer table items not always spoken/displayed
112		GNOME 2.20	354470	nor	Nor	[requirement] Grade 2 Braille
113		GNOME 2.20	400718	enh	Nor	[requirement] Braille: Effective presentation of white space.
114		GNOME 2.20	354471	min	Nor	[requirement] Text selection from braille input device
115	Rich	GNOME 2.20	376015	nor	Nor	[a11y] time-admin time servers table is not accessible.
116		GNOME 2.20	424528	enh	Nor	Script support for gnucash.
117		GNOME 2.20	424531	enh	Nor	Script support for Rhythmbox.
118		GNOME 2.20	363820	enh	Nor	[blocked] Orca should inform the user when text in given cell in Calc is too wide for that column
119	Willie	TBS	434654	nor	Nor	Orca skips a line in flat review mode or with braille navigation (braille up / down).
120	Rich	GNOME 2.20	397668	nor	Nor	Blank lines are not announced as blank lines in gnome-terminal
121		GNOME 2.20?	400729	nor	Nor	[requirement] Orca should provide support for general audio
122		GNOME 2.20?	354474	min	Nor	[requirement] Audio cues when crossing line boundaries
123		GNOME 2.20?	350742	nor	Nor	[blocked] text from text boxes not reported all the time in java applications
124	Lynn	TBS	407704	nor	Nor	jedit does not speak or braille text in composition area
125		GNOME 2.20?	424529	enh	Nor	Script support for Planner.
126		TBS	419136	nor	Nor	[blocked] Planner toggle button in main window not accessible
127		TBS	419137	nor	Nor	[blocked] planner Edit Task Properties dialog has broken accessible component hierarchy
128		TBS	419138	nor	Nor	[blocked] In planner, toggle button on end of "Ribbon" doesn't have accessible name/description
129		TBS	434594	min	Nor	status of controls not shown by orca in flat review mode
130	Rich	GNOME 2.20?	376515	enh	Nor	Add GUI support for the new customizable text-attribute feature
131		GNOME 2.22	431531	enh	Nor	Add support for user-configurable character naming
132		GNOME 2.20?	424522	enh	Nor	Script support for a bittorrent client.
134	Mike Spec	GNOME 2.20?	354459	min	Nor	[requirement] Verbalized caps
135		GNOME 2.20?	363793	enh	Nor	Add the ability to change the color of the flat review rectangle
136	Ask List	TBS	412656	enh	Nor	Refactor speech generators to provide ACSS per string
137		GNOME 2.20?	424525	enh	Nor	Script support for gnome-blogger.
138		GNOME 2.20?	371637	nor	Nor	[blocked] Orca repeats "Location:" info repeatedly in Nautilus File Browser Dialog
139		GNOME 2.20?	365284	nor	Nor	[blocked] Evolution's account wizard Welcome message will not be reported by orca
140		GNOME 2.20?	424524	enh	Nor	Script support for gftp.
141	Rich	GNOME 2.20?	395146	nor	Nor	Crash at start
142		TBS	373387	enh	Low	Users should be able to lock/unlock the "Lock" modifier even if Caps Lock is the Orca modifier
143	Joanie	GNOME 2.20?	387556	enh	Low	Arrowing past last character at end of line in Orca results in no speech
144	Rich	TBS	400711	nor	Nor	Month view is inaccessible in Evolution calendar.
145		TBS	400732	enh	Nor	[requirement] Toggle between logical and screen braille presentations.
146	Willie/Rich	TBS	373078	min	Low	Unable to change voice in application specif settings file.
147		TBS	356068	enh	Nor	[blocked] Provide a command for identifying the default button within a dialog
148		TBS	354462	min	Nor	[requirement] SayAll of dialogs (versus just a single text area)
149		TBS	319659	enh	Low	Automatic documentation for keybinds script.
150		TBS	364765	nor	Nor	[blocked] Escaping out of Wizards submenu in OOo Writer causes Orca to report "Format menu"
151		TBS	408430	nor	Nor	COMM_FAILURE when running simple Gtk application
152		TBS	407647	nor	Nor	[blocked] Indicate the tree level of items in the Gaim (post 2.0 beta 3.1) buddy list
153		TBS	355524	nor	Nor	[blocked] Flatreview doesn't work in gnome-about panel.
154		TBS	434780	nor	Nor	[blocked] Orca does not provide access to text attributes in Firefox
156	Rich	TBS	412359	enh	Nor	Better integration with bug buddy.
157		TBS	423440	enh	Nor	Permit reloading of scripts while Orca is running
158	Willie	TBS	415201	nor	Nor	Mouse cusor will not change its shape in magnified screen.
159		TBS	431418	tri	Low	Orca abruptly terminates if it wants to open debug.out in a directory that it doesn't have write permission for.
160		TBS	354433	enh	Low	Add feature to notify user when a new version is available
161		TBS	419142	nor	Nor	[blocked] The accessible name for Evolution mail message header list "checkbox" table cells is not useful
162		TBS	353446	nor	Nor	[blocked] Orca not correctly reporting key values in gconf-editor
163	Willie	TBS	349394	enh	Nor	Speech Dispatcher Backend
999	Lynn	TBS	436658	nor	Nor	flat-review speaks "filler" for SwingSet2 demo/source tabs
999	Lynn	TBS	435908	nor	Nor	Orca does not speak Sun Download Manager download status when it changes
999	Lynn	TBS	435900	nor	Nor	Orca speak raw HTML in Sun Download Manager Hints dialog
999		TBS	436641	enh	Nor	Flat review does not refresh itself in some cases
999		TBS	436391	nor	Nor	[blocked] Querying the value of the progress bar in Firefox crashes Firefox
999	Lynn	TBS	435585	nor	Nor	Java ControlPanel GIVING UP AFTER 5 TRIES Advanced Settings tree table
999	Lynn	TBS	435567	nor	Nor	Java ControlPanel AttributeError: 'NoneType' object has no attribute 'getNSelections' traceback
999	Lynn	TBS	435898	maj	Nor	[blocked] LABEL_FOR relations not set in Sun Download Manager's Set Options and Proxies" dialog
999		TBS	435852	cri	Nor	Orca and OpenOffice Calc have a memory lovefest.
999		TBS	434940	nor	Nor	[blocked] Orca does not speak page tabs in the Java Control Panel
999		TBS	437004	enh	Nor	[pending] Add in hooks for allowing activation/deactivation script methods.
999		TBS	436926	enh	Nor	Keyboard bindings should be more easily definable for different locales
999	Lynn	TBS	437226	nor	Nor	Orca should handle Java labels and text where LABEL_FOR is not set
999	Lynn	TBS	437049	nor	Nor	Orca does not speak Java Control Panel spinbox changes
999	Lynn	TBS	436664	nor	Nor	Cannot flat-review SwingSet2 JEditorPane or JTextArea
999	Lynn	TBS	436661	nor	Nor	flat-review speaks SwingSet2 toolbar image paths instead of item names
999		TBS	436888	enh	Nor	Include widget status information in braille for flat review
999	Lynn	TBS	436674	nor	Nor	flat-review only visits right-most tree nodes in SwingSet2 JTree demo
999	Lynn	TBS	435283	nor	Nor	Orca does not braille Eclipse workbench tab panes
999	Lynn	TBS	435267	nor	Nor	Orca does not speak hyperlinks in Eclipse dialogs
999	Lynn	TBS	435301	cri	Nor	NetBeans installation is not accessible with Orca
999	Lynn	TBS	435290	nor	Nor	Orca does not speak the Eclipse Help Contents frame-
999	Lynn	TBS	435253	nor	Nor	orca does not speak static text in Eclipse dialogs
999		TBS	435201	nor	Nor	Orca is too chatty when navigating by paragraph in OOo Writer
999		TBS	435199	cri	Nor	Orca is bloating the swap partition, so the system is no more usable after a short time.
999		TBS	435247	nor	Nor	orca_gui_prefs.py traceback running orca --setup
999		TBS	435226	nor	Nor	Where-am-I doesn't correctly handle multiple selected paragraphs in OOo Writer and Evolution.
999	Lynn	TBS	435553	nor	Nor	KeyError: 'startOffset' during Java ControlPanel flat-review
999	Lynn	TBS	435535	nor	Nor	Orca does not speak static text in java ControlPanel tab pages
999	Lynn	TBS	435565	nor	Nor	Java ControlPanel AttributeError: 'NoneType' object has no attribute 'getTextAtOffset'
999	Lynn	TBS	435308	maj	Nor	Orca does not speak NetBeans main window contents
999	Lynn	TBS	435349	nor	Nor	Ctrl-C does not stop endless speech in NetBeans program editor
999	Lynn	TBS	435353	nor	Nor	"where am I" does not speak information about any NetBeans components
999	Lynn	TBS	435563	nor	Nor	[blocked] LABEL_FOR relations not set in Java Control Panel "Temporary Files Settings" page
999	Lynn	TBS	435354	nor	Nor	flat-review does not work in NetBeans
999		TBS	433818	enh	Low	Messages on system tab of gnome-system-monitor are not reported by orca.