## Sheet1
Rank	Who	Target	Sev	Pri	ID	Summary
1	FF METABUG		maj	Hig	404403	Firefox Metabug
2	Joanie	GNOME 2.19.5	maj	Nor	407941	Infer labels for objects in HTML content
3	Joanie		nor	Nor	407663	[blocked] Support the "Find" operation in Firefox better
4	Joanie	GNOME 2.19.2	maj	Hig	423534	[blocked] structural navigation should not get stuck on slashdot.org
5	Joanie	GNOME 2.19.1	nor	Nor	411261	Some HTML constructs cause Orca to say just "Link" when arrowing up and down by line
6	Mike		maj	Nor	423224	[blocked] Firefox should not crash while submitting bugs in Bugzilla with Orca running
7	Willie	GNOME 2.19.2	maj	Nor	412677	[blocked] Navigation to links with { overflow:hidden } stylesheet results in bad behavior
8	Willie	GNOME 2.19.2	nor	Nor	423435	Orca is too chatty when loading a page in Firefox
9	Joanie	GNOME 2.19.2	nor	Nor	413990	[blocked] orca should not speak table over and over again when tabbing through a web page
10			nor	Nor	414762	[blocked] Control Home/End, Up/Down Arrow don't always work in Firefox
11	Joanie	GNOME 2.19.4	nor	Nor	423427	Need to add form field structural navigation in Firefox
12	Joanie	GNOME 2.19.1	nor	Nor	416971	[blocked] Orca does not speak or braille numbers/bullets of list items in Firefox
13	Joanie		nor	Nor	422924	[blocked] Add more support for accessing HTML tables in Firefox
14	Willie	GNOME 2.19.90	nor	Nor	423348	Support DHTML, AJAX, ARIA in Firefox/Gecko
15	Willie/Solaris		nor	Nor	423354	Keyboard navigation broken on http://www.blindcooltech.com/
16	Joanie	TBS	nor	Nor	428025	Links should not be spoken twice when down arrowing in firefox
17	Joanie	TBS	nor	Nor	428114	Orca sometimes misidentifies combo box contents as the name in Firefox
18	Joanie	TBS	enh	Nor	414657	Linked headings should be announced as both heading and link
19	Willie	TBS	nor	Nor	414738	Flat review in Firefox doesn't start at caret position
20	Joanie	TBS	nor	Nor	427722	Web page separators cause Orca to get stuck with go{Next,Previous}Line
21	Joanie	TBS	nor	Nor	426360	SayAll is broken in Firefox
22	Willie	TBS	nor	Nor	416017	[blocked] FF3 and Orca error reading a page footer
23	Rich	GNOME 2.19.90	enh	Nor	400716	[pending] sayAll should be done by sentences.
24	Willie	GNOME 2.19.1	maj	Nor	412200	Orca L10N / Translation issues
25	Willie	TBS	nor	Nor	418147	[pending] Error spelling words or lines
26	Lynn	GNOME 2.19.1	nor	Nor	412837	Orca needs test code coverage reporting
27	Lynn	GNOME 2.19.1	maj	Nor	415061	regression test results should be repeatable
28	Lynn		nor	Nor	416332	Orca test coverage needs to be extended
29	Lynn	GNOME 2.20!	enh	Nor	368640	Allow user to optionally ignore or be notified of tool tips
30	Lynn	GNOME 2.20!	nor	Nor	354479	[blocked] [requirement] Automatic presentation of "balloon" type messages
31	Rich	GNOME 2.20	nor	Nor	404411	OpenOffice Metabug
32	Rich	GNOME 2.20!	min	Nor	356066	[blocked] Items in OOo's Navigator window are not always spoken
33	Rich	GNOME 2.20!	enh	Nor	356060	[blocked] Provide access to tree item level and state in OOo Navigator
34	Rich	TBS	nor	Nor	413909	[blocked] Orca can no longer provide "smarts" for spell checking in OOo Writer v2.1 (or later)
35	Rich	GNOME 2.20!	enh	Nor	363827	[blocked] Insert F should provide access to the style and font name in OOo Writer
36	Mike Spec	GNOME 2.20!	enh	Nor	372965	[blocked] Insert F should provide access to ALL attributes applied to text in OOo Writer
37	Joanie	GNOME 2.20!	enh	Nor	363830	[blocked] Provide feedback in OOo when toggling bold, underline, and italics
38	Rich	GNOME 2.20!	enh	Nor	404046	[blocked] Provide feedback in OOo when a command changes attributes
39	Rich	GNOME 2.20!	nor	Nor	376517	[blocked] Orca does not report indentation in OOo Writer documents correctly
40	Rich	GNOME 2.20!	maj	Nor	361737	[blocked] It is not possible to navigate to form controls using the keyboard in OOo Writer
41	Rich	TBS	nor	Nor	412252	[blocked] OOo Writer crash when using Orca
42	Rich	TBS	nor	Nor	429390	Braille stays on current line after pressing return at end of line in OOo Writer
43	Rich	TBS	enh	Nor	426010	Implement verbalized links in OOo
44		GNOME 2.20?	nor	Nor	364772	[blocked] Orca can not detect miss-spelled words on the fly in Openoffice
45	Rich	GNOME 2.20	enh	Nor	372273	Add ability to configure app-specific settings via GUI
46	Mike	GNOME 2.20!	enh	Nor	382601	Orca should indicate selected text on the braille display
47	Mike Spec	GNOME 2.20!	enh	Nor	400720	[requirement] Support accurate presentation of text attributes on the braille display
48		TBS	nor	Nor	419139	[blocked] Gnome Screen saver password dialog not accessible
49	Rich	GNOME 2.20?	nor	Nor	354466	[requirement] Watched Objects
50	Rich	GNOME 2.20?	min	Nor	354468	[requirement] Bookmarked Objects
51			cri	Nor	423323	[blocked] Thunderbird 3.0-a1 crashes every time I close a message.
52			nor	Nor	423346	Evolution Metabug
53		TBS	nor	Nor	349978	[blocked] Orca does not announce a message change when deleting a message in evolution
54		TBS	nor	Nor	353470	[blocked] Orca does not speak when the last message in the Evolution mail message header summary list is deleted.
55	Lynn	TBS	nor	Nor	427481	"where am I" does not speak Evolution Mail...Tasks toggle buttons
56		TBS	nor	Nor	419141	[blocked] When deleting messages in Evolution, Orca initially speaks the wrong tree item
57		TBS	nor	Nor	353458	[blocked] Text selection in Evolution "New Message" text area is not reported.
58			enh	Nor	422487	[blocked] Ability to jump to the start of the message in Evolution.
59		TBS	nor	Nor	424149	Evolution mail message window inconsistent with item selected in mail header list.
60		TBS	nor	Nor	353434	[blocked] Backspaced characters in the 'subject' and 'to' lines of evolution are not announced.
61		TBS	nor	Nor	401889	[blocked] Orca does not speak backspaced characters in certain dialogs
62	Rich	GNOME 2.20?	enh	Nor	364518	Create a GUI interface to the pronunciation dictionary.
63	Joanie	GNOME 2.20?	enh	Nor	425563	[blocked] Provide structural navigation of PDF documents
64		TBS	nor	Nor	423436	RealPlayer doesn't seem to work well with Orca
65		TBS	nor	Nor	407658	[blocked] Cannot access status bar information in Gedit
66	Willie	TBS	enh	Nor	419742	Add it the ability to switch languages.
67	Lynn		nor	Nor	420324	Problems building Access Bridge v1.5.0
68	Willie	TBS	enh	Nor	405759	Distinguish Q and BLOCKQUOTE in (X)HTML content
69	Willie	GNOME 2.20!	nor	Nor	345399	Key echo missing alpha numeric and punctuation keys.
70		TBS	nor	Nor	402835	[blocked] In Firefox 3.0 a submenu of the bookmarks menu cannot be accessed, if speech is activated.
71	Rich		enh	Nor	422475	Orca should speak the word deleted if You enter Control-Backspace.
72	Rich	GNOME 2.18!	nor	Hig	404409	Thunderbird Metabug
73	Willie/Rich	TBS	nor	Nor	409728	Orca repeats mouse-selected text numerous times in thunderbird
74	Rich	TBS	enh	Nor	409736	[blocked] Orca does not announce the beginning of strings pasted into thunderbird
75		TBS	nor	Nor	374537	[blocked] Thunderbird 3.0 checkbox table cells in subscribe dialog do not provide checked/unchecked state
76		TBS	nor	Nor	373135	[blocked] Thunderbird 3.0 add-on dialog buttons not spoken
77		GNOME 2.18!	maj	Hig	354467	Opening URL in Freeloader hangs Orca
78	Willie	GNOME 2.20!	maj	Hig	NO ID	Accessible Installation of Solaris Express
79	Joanie	TBS	nor	Nor	412100	Text selection in Firefox fails when Orca controls the caret
80	Willie	GNOME 2.20!	nor	Nor	404422	Support per-URL Scripts
81	Lynn	TBS	nor	Nor	410088	NetworkManager applet not spoken when network is disconnected
82		GNOME 2.20!	nor	Nor	352163	[blocked] Orca announces incorrect info in Deskbar Applet
83	Rich	TBS	enh	Nor	409731	Orca should speak text selected by the mouse
84	Willie	TBS	nor	Nor	375782	The performance of orca full screen magnification is not good.
85	Willie	TBS	nor	Nor	375396	Orca failed to exit after stopping the full screen mag.
86	Willie	TBS	cri	Nor	399639	Orca crashes and magnifier hangs if user enables the magnifier.
87	Willie	TBS	nor	Nor	403760	Emacspeak speech factory doesn't always shutdown/restart correctly
88	Willie	TBS	maj	Nor	355525	Orca skipped one line of web content in flatreview mode.
89		GNOME 2.20!	nor	Nor	383120	[blocked] Ekiga conversation message cannot be read by orca
90		GNOME 2.20!	nor	Nor	354782	[blocked] gnome-system-monitor "Resources" tab is inaccessible
91		GNOME 2.20!	nor	Nor	356041	Previous link in desktop helper can not be read by orca.
92		GNOME 2.20!	nor	Nor	356042	[blocked] The labels in File Management Preferences (nautilus-file-management-properties) window were not reported by orca.
93		GNOME 2.20!	nor	Nor	397680	[blocked] OOo Writer Save As Encoded Text throws up a dialog that is not properly spoken
94		GNOME 2.20!	nor	Nor	385828	[blocked] Can not use agenda wizard in OpenOffice.org
95		GNOME 2.20!	nor	Nor	357545	[blocked] Orca does not speak all buttons in openoffice database table creation wizzard
96	Willie	GNOME 2.20?	enh	Nor	400717	Orca should support multi-lingual text.
97	Willie	TBS	enh	Nor	397306	Orca's default synthesis engine choice should take language into account
98	Mike/Joanie Spec	GNOME 2.20	nor	Nor	400728	[requirement] Orca should provide a means to quickly set often-used preferences
99		TBS	nor	Nor	347691	[blocked] In standard print dialog, printer table items not always spoken/displayed
100		GNOME 2.20	nor	Nor	354470	[requirement] Grade 2 Braille
101		GNOME 2.20	enh	Nor	400718	[requirement] Braille: Effective presentation of white space.
102		GNOME 2.20	min	Nor	354471	[requirement] Text selection from braille input device
103	Rich	GNOME 2.20	nor	Nor	376015	[a11y] time-admin time servers table is not accessible.
104		GNOME 2.20	enh	Nor	424528	Script support for gnucash.
105		GNOME 2.20	enh	Nor	424531	Script support for Rhythmbox.
106		GNOME 2.20	enh	Nor	363820	[blocked] Orca should inform the user when text in given cell in Calc is too wide for that column
107	Rich	GNOME 2.20	nor	Nor	397668	Blank lines are not announced as blank lines in gnome-terminal
108		GNOME 2.20?	nor	Nor	400729	[requirement] Orca should provide support for general audio
109		GNOME 2.20?	min	Nor	354474	[requirement] Audio cues when crossing line boundaries
110		GNOME 2.20?	nor	Nor	350742	[blocked] text from text boxes not reported all the time in java applications
111	Lynn	TBS	nor	Nor	407704	jedit does not speak or braille text in composition area
112		GNOME 2.20?	enh	Nor	424529	Script support for Planner.
113	Rich	GNOME 2.20?	enh	Nor	376515	Add GUI support for the new customizable text-attribute feature
114		GNOME 2.20?	enh	Nor	424522	Script support for a bittorrent client.
115		GNOME 2.20?	enh	Nor	363804	Add ability to turn off coordinate announcement when navigating in Calc
116	Mike Spec	GNOME 2.20?	min	Nor	354459	[requirement] Verbalized caps
117		GNOME 2.20?	enh	Nor	363793	Add the ability to change the color of the flat review rectangle
118	Ask List	TBS	enh	Nor	412656	Refactor speech generators to provide ACSS per string
119		GNOME 2.20?	enh	Nor	424525	Script support for gnome-blogger.
120		GNOME 2.20?	nor	Nor	371637	[blocked] Orca repeats "Location:" info repeatedly in Nautilus File Browser Dialog
121		GNOME 2.20?	nor	Nor	365284	[blocked] Evolution's account wizard Welcome message will not be reported by orca
122		GNOME 2.20?	enh	Nor	424524	Script support for gftp.
123	Rich	GNOME 2.20?	nor	Nor	395146	Crash at start
124		TBS	enh	Low	373387	Users should be able to lock/unlock the "Lock" modifier even if Caps Lock is the Orca modifier
125	Joanie	GNOME 2.20?	enh	Low	387556	Arrowing past last character at end of line in Orca results in no speech
126	Rich	TBS	nor	Nor	400711	Month view is inaccessible in Evolution calendar.
127		TBS	enh	Nor	400732	[requirement] Toggle between logical and screen braille presentations.
128	Willie/Rich	TBS	min	Low	373078	Unable to change voice in application specif settings file.
129		TBS	enh	Nor	356068	[blocked] Provide a command for identifying the default button within a dialog
130		TBS	min	Nor	354462	[requirement] SayAll of dialogs (versus just a single text area)
131		TBS	enh	Low	319659	Automatic documentation for keybinds script.
132		TBS	enh	Low	319752	Orca should support multiline braille displays
133		TBS	nor	Nor	364765	[blocked] Escaping out of Wizards submenu in OOo Writer causes Orca to report "Format menu"
134		TBS	nor	Nor	408430	COMM_FAILURE when running simple Gtk application
135		TBS	nor	Nor	407647	[blocked] Indicate the tree level of items in the Gaim (post 2.0 beta 3.1) buddy list
136		TBS	nor	Nor	355524	[blocked] Flatreview doesn't work in gnome-about panel.
137		TBS	nor	Nor	362627	[blocked] Thunderbird folder properties: no relationship between page tabs and page contents
138		TBS	enh	Low	354433	Add feature to notify user when a new version is available
139		TBS	nor	Nor	353446	[blocked] Orca not correctly reporting key values in gconf-editor
140	Willie	TBS	enh	Nor	349394	Speech Dispatcher Backend
999			nor	Nor	381455	[blocked] Thunderbird does not present labels around dialog text entries
999	Rich	TBS	enh	Nor	412359	Better integration with bug buddy.
999	Willie	TBS	enh	Nor	412661	Gecko.py: determine isUselessObject vs. isLayoutOnly relationship
999		TBS	maj	Nor	412829	[blocked] Cannot identify selected text in Firefox or Thunderbird
999	Willie	TBS	nor	Nor	415201	Mouse cusor will not change its shape in magnified screen.
999		TBS	nor	Nor	415812	[blocked] Orca sometimes provides incorrect information regarding table headers
999		TBS	nor	Nor	418287	[blocked] Treat words separated by non-breaking spaces as a single word in OOo
999	Willie	TBS	nor	Nor	419123	Modified speech settings do not change immediately in preferences dialog
999		TBS	nor	Nor	419135	[blocked] Tables with column headers have accessibility issues
999		TBS	nor	Nor	419136	[blocked] Planner toggle button in main window not accessible
999		TBS	nor	Nor	419137	[blocked] planner Edit Task Properties dialog has broken accessible component hierarchy
999		TBS	nor	Nor	419138	[blocked] In planner, toggle button on end of "Ribbon" doesn't have accessible name/description
999		TBS	nor	Nor	419142	[blocked] The accessible name for Evolution mail message header list "checkbox" table cells is not useful
999			enh	Nor	420540	Firefox keyboard control wish list.
999		TBS	enh	Nor	423440	Permit reloading of scripts while Orca is running
999		TBS	nor	Nor	427876	Orca hangs in linphone and ekiga soft phone