## Sheet1
Rank	Who	Target	Sev	Pri	ID	Summary
1	Willie	TBS	maj	Nor	405616	Orca failed to report the combobox menu.
2	Joanie	GNOME 2.18!	maj	Hig	404403	Firefox 3.0 - most web pages, but no guarantees on DHTML, Lockhart, AJAX
3		TBS	nor	Nor	385949	[blocked] Orca has traceback with Firefox 3.0 nightly when testing bookmarks.
4	Willie/Rich	TBS	nor	Nor	342131	[requirement] Implement verbalized links
5		TBS	nor	Nor	402835	[blocked] In Firefox 3.0 a submenu of the bookmarks menu cannot be accessed, if speech is activated.
6	Rich	GNOME 2.18!	maj	Hig	404409	Thunderbird
7	Willie/Rich	TBS	nor	Nor	409728	Orca repeats mouse-selected text numerous times in thunderbird
8	Rich	TBS	enh	Nor	409736	Orca does not announce the beginning of strings pasted into thunderbird
9		TBS	nor	Nor	374537	[blocked] Thunderbird 3.0 checkbox table cells in subscribe dialog do not provide checked/unchecked state
10		TBS	nor	Nor	373135	[blocked] Thunderbird 3.0 add-on dialog buttons not spoken
11		GNOME 2.18!	maj	Hig	354467	Opening URL in Freeloader hangs Orca
12	Willie	GNOME 2.18!	enh	Nor	408670	Braille and speech don't track well in text entry areas in Firefox and Thunderbird
13	Joanie	GNOME 2.18!	enh	Nor	407948	{Shift+}o and {Shift+}h do not work reliably in Firefox
14	Rich	GNOME 2.20!	enh	Nor	395548	Refactor calls to util.py as calls from delegates in default.py
15	Rich	GNOME 2.20!	enh	Low	402494	For statement refactoring.
15.5	Ask List	TBS	enh	Nor	412656	Refactor speech generators to provide ACSS per string
15.6	Rich	TBS	min	Nor	413109	HIG violations
16	Willie	GNOME 2.20!	maj	Nor	412200	Orca L10N / Translation issues
17	Rich	GNOME 2.19.0	enh	Nor	350674	make orca announce when a new folder is opened and announce number of items
18	Willie	GNOME 2.20!	nor	Nor	345399	Key echo missing alpha numeric and punctuation keys.
19	Rich	TBS	enh	Nor	410302	Better support for gnome-mud application
20	Joanie	GNOME 2.19.1	enh	Nor	407941	Infer labels for objects in HTML content
21	Willie	GNOME 2.20!	maj	Hig	NO ID	Accessible Installation of Solaris Express
22	Joanie	TBS	nor	Nor	407663	Support the "Find" operation in Firefox better
23	Willie/Joanie	TBS	nor	Nor	411261	Some HTML constructs cause Orca to say just "Link" when arrowing up and down by line
24	Joanie	TBS	nor	Nor	412100	Text selection in Firefox fails when Orca controls the caret
25	Joanie	GNOME 2.20!	maj	Hig	404403	Firefox 3.0 - evaluation of DHTML, Lockhart, AJAX
26	Rich	GNOME 2.19.0	enh	Nor	404052	Say something to let the user know the Preferences dialog is loading
27	Willie	GNOME 2.20!	maj	Hig	404422	Support per-URL Scripts
28	Willie/Close	TBS	enh	Nor	354970	Support customization of key and braille bindings
29		TBS	nor	Nor	353434	[blocked] Backspaced characters in the 'subject' and 'to' lines of evolution are not announced.
30		TBS	nor	Nor	401889	[blocked] Orca does not speak backspaced characters in certain dialogs
31		GNOME 2.20!	nor	Nor	354479	[blocked] [requirement] Automatic presentation of "balloon" type messages
32	Lynn	TBS	nor	Nor	410088	NetworkManager applet not spoken when network is disconnected
33		GNOME 2.20!	nor	Nor	352163	[blocked] Orca announces incorrect info in Deskbar Applet
34		GNOME 2.20!	enh	Nor	363827	[blocked] Insert F should provide access to the style and font name in OOo Writer
35		GNOME 2.20!	enh	Nor	372965	[blocked] Insert F should provide access to ALL attributes applied to text in OOo Writer
36		GNOME 2.20!	enh	Nor	363830	[blocked] Provide feedback in OOo when toggling bold, underline, and italics
37		GNOME 2.20!	enh	Nor	404046	[blocked] Provide feedback in OOo when a command changes attributes
38		GNOME 2.20!	nor	Nor	376517	[blocked] Orca does not report indentation in OOo Writer documents correctly
39		GNOME 2.20!	maj	Nor	361737	[blocked] It is not possible to navigate to form controls using the keyboard in OOo Writer
40	Rich/Close	GNOME 2.20!	nor	Nor	400712	Orca doesn't provide compelling access to ooimpress
41		GNOME 2.20!	nor	Nor	368626	[blocked] Orca accessing tool tips from gnome-panel causes gnome-panel to crash
42		GNOME 2.20!	nor	Nor	368640	[blocked] Orca should present tool tips when they are popped up
43	Lynn	GNOME 2.20!	enh	Nor	398009	Orca should be able to provide tooltip text for an object
44	Mike	GNOME 2.20!	enh	Nor	382601	Orca should indicate selected text on the braille display
45	Rich	TBS	enh	Nor	409731	Orca should speak text selected by the mouse
46	Mike Spec	GNOME 2.20!	enh	Nor	400720	[requirement] Support accurate presentation of text attributes on the braille display
47	Rich	TBS	nor	Nor	402192	Orca does not speak text that is pasted in by middle mouse click.
48	Willie	TBS	nor	Nor	375782	The performance of orca full screen magnification is not good.
49	Willie	TBS	nor	Nor	375396	Orca failed to exit after stopping the full screen mag.
50	Willie	TBS	cri	Nor	399639	Orca crashes and magnifier hangs if user enables the magnifier.
51	Willie	TBS	nor	Nor	403760	Emacspeak speech factory doesn't always shutdown/restart correctly
52	Mike Spec	GNOME 2.20!	enh	Nor	400716	[requirement] sayAll should be done by sentences.
53		GNOME 2.20!	maj	Hig	408071	[blocked] Flat review of Firefox reveals content from all tabs
54	Willie	TBS	maj	Nor	355525	Orca skipped one line of web content in flatreview mode.
55		GNOME 2.20!	nor	Nor	383120	[blocked] Ekiga conversation message cannot be read by orca
56		TBS	nor	Nor	353458	[blocked] Text selection in Evolution "New Message" text area is not reported.
57		TBS	nor	Nor	352086	[blocked] Orca stops speaking items in Evolution's Select a Folder dialog if you start typing
58		TBS	nor	Nor	353468	[blocked] Orca not always reporting expanded state of Evolution mail tree items.
59		TBS	nor	Nor	353470	[blocked] Orca does not speak when the last message in the Evolution mail message header summary list is deleted.
60		TBS	nor	Nor	349978	[blocked] Orca does not announce a message change when deleting a message in evolution
61		GNOME 2.20!	nor	Nor	354782	[blocked] gnome-system-monitor "Resources" tab is inaccessible
62		GNOME 2.20!	nor	Nor	356041	Previous link in desktop helper can not be read by orca.
63		GNOME 2.20!	nor	Nor	356042	[blocked] The labels in File Management Preferences (nautilus-file-management-properties) window were not reported by orca.
64		GNOME 2.20!	nor	Nor	397680	[blocked] OOo Writer Save As Encoded Text throws up a dialog that is not properly spoken
65		GNOME 2.20!	nor	Nor	385828	[blocked] Can not use agenda wizard in OpenOffice.org
66		TBS	nor	Nor	407658	[blocked] Cannot access status bar information in Gedit
67		GNOME 2.20!	nor	Nor	357545	[blocked] Orca does not speak all buttons in openoffice database table creation wizzard
68		GNOME 2.20!	min	Nor	356066	[blocked] Items in OOo's Navigator window are not always spoken
69		GNOME 2.20!	enh	Nor	356060	[blocked] Provide access to tree item level and state in OOo Navigator
70	Willie	GNOME 2.20?	enh	Nor	400717	Orca should support multi-lingual text.
71	Willie	TBS	enh	Nor	397306	Orca's default synthesis engine choice should take language into account
72	Mike/Joanie Spec	GNOME 2.20	nor	Nor	400728	[requirement] Orca should provide a means to quickly set often-used preferences
73		TBS	nor	Nor	347691	[blocked] In standard print dialog, printer table items not always spoken/displayed
74		GNOME 2.20	nor	Nor	354470	[requirement] Grade 2 Braille
75		GNOME 2.20	enh	Nor	400718	[requirement] Braille: Effective presentation of white space.
76		GNOME 2.20	min	Nor	354471	[requirement] Text selection from braille input device
77	Rich	GNOME 2.20	enh	Nor	372273	Add ability to configure app-specific settings via GUI
78	Rich	GNOME 2.20	nor	Nor	376015	[a11y] time-admin time servers table is not accessible.
79	Rich/OPEN	GNOME 2.20	nor	Nor	NO ID	Support for gnucash
80	Rich/OPEN	GNOME 2.20	nor	Nor	NO ID	Support for Rhythmbox
81	BLOCKED?	TBS	cri	Nor	405613	Totem crashes when user open files while orca running.
82		GNOME 2.20	enh	Nor	363820	[blocked] Orca should inform the user when text in given cell in Calc is too wide for that column
83	Rich	GNOME 2.20	nor	Nor	397668	Blank lines are not announced as blank lines in gnome-terminal
84		GNOME 2.20?	nor	Nor	400729	[requirement] Orca should provide support for general audio
85		GNOME 2.20?	min	Nor	354474	[requirement] Audio cues when crossing line boundaries
86		GNOME 2.20?	nor	Nor	350742	[blocked] text from text boxes not reported all the time in java applications
87	Lynn	TBS	nor	Nor	407704	jedit does not speak or braille text in composition area
88	Rich/OPEN	GNOME 2.20?	nor	Nor	NO ID	Support for Planner
89	Rich	GNOME 2.20?	enh	Nor	376515	Add GUI support for the new customizable text-attribute feature
90	Rich/OPEN	GNOME 2.20?	nor	Nor	NO ID	Support for a bittorrent client.
91		GNOME 2.20?	enh	Nor	363804	Add ability to turn off coordinate announcement when navigating in Calc
92	Rich	GNOME 2.20?	enh	Nor	364518	Create a GUI interface to the pronunciation dictionary.
93	Willie	TBS	enh	Nor	405759	Distinguish Q and BLOCKQUOTE in (X)HTML content
94	Mike Spec	GNOME 2.20?	min	Nor	354459	[requirement] Verbalized caps
95		GNOME 2.20?	enh	Nor	363793	Add the ability to change the color of the flat review rectangle
96		GNOME 2.20?	min	Nor	354464	[requirement] Jump to well-known object
97		GNOME 2.20?	nor	Nor	354466	[requirement] Watched Objects
98		GNOME 2.20?	min	Nor	354468	[requirement] Bookmarked Objects
99		TBS	enh	Nor	400715	[requirement] Extend the Find command for HTML web content.
100	Rich/OPEN	GNOME 2.20?	nor	Nor	NO ID	Support for gnome-blogger
101		GNOME 2.20?	nor	Nor	364772	[blocked] Orca can not detect miss-spelled words on the fly in Openoffice
102		GNOME 2.20?	nor	Nor	371637	[blocked] Orca repeats "Location:" info repeatedly in Nautilus File Browser Dialog
103		GNOME 2.20?	nor	Nor	365284	[blocked] Evolution's account wizard Welcome message will not be reported by orca
104	Rich/OPEN	GNOME 2.20?	nor	Nor	NO ID	Support for gftp
105	Rich	GNOME 2.20?	nor	Nor	395146	Crash at start
106		TBS	enh	Low	373387	Users should be able to lock/unlock the "Lock" modifier even if Caps Lock is the Orca modifier
107	Joanie	GNOME 2.20?	enh	Low	387556	Arrowing past last character at end of line in Orca results in no speech
108	Rich	TBS	nor	Nor	400711	Month view is inaccessible in Evolution calendar.
109		TBS	enh	Nor	400732	[requirement] Toggle between logical and screen braille presentations.
110	Willie/Rich	TBS	nor	Low	373078	Unable to change voice in application specif settings file.
111		TBS	enh	Nor	356068	[blocked] Provide a command for identifying the default button within a dialog
112	Willie/Close	TBS	enh	Nor	399901	using ctrl + scrolling of mouse = magnified
113		TBS	min	Nor	354462	[requirement] SayAll of dialogs (versus just a single text area)
114	Willie/Close	TBS	enh	Low	319659	Automatic documentation for keybinds script.
115	Willie/Close	TBS	enh	Low	319779	Need to define what speech and mouse input events look like
116		TBS	enh	Low	319752	Orca should support multiline braille displays
117	Willie/Close	TBS	enh	Nor	319778	src/orca/hierarchical_presenter.py: need to determine if this is supported or not
118		TBS	nor	Nor	364765	[blocked] Escaping out of Wizards submenu in OOo Writer causes Orca to report "Format menu"
119	Rich	GNOME 2.20	nor	Nor	404411	[blocked] OOo Writer crash when using Orca
120		TBS	nor	Nor	408430	COMM_FAILURE when running simple Gtk application
121	Willie/Close	TBS	enh	Nor	319771	src/orca/flat_review.py:getZonesFromAccessible should optimize for text that is visible
122	Willie/Close	TBS	nor	Nor	406902	flat_review.py:visible can return false positives
123		TBS	enh	Nor	406874	Minor efficiency enhancements for flat_review.py:getZonesFromText
124	Lynn	TBS	nor	Nor	405815	Many OOo Writer Unmapped Keycode warnings
125		TBS	enh	Nor	407647	[blocked] Indicate the tree level of items in the Gaim (post 2.0 beta 3.1) buddy list
126		TBS	nor	Nor	355524	[blocked] Flatreview doesn't work in gnome-about panel.
127	Willie/Close	TBS	nor	Nor	319770	src/orca/flat_review.py:getZonesFromAccessible should clip zones based on what text is visible
128		TBS	blo	Nor	362627	[blocked] Thunderbird folder properties: no relationship between page tabs and page contents
129	Willie/Close	TBS	enh	Nor	319740	Efficiency concerns in src/orca/atspi.py:findBy{Role,Name}
130	Mike/Close	TBS	enh	Nor	411213	Inform the user what happened when they pressed a button
131	Willie/Close	TBS	min	Low	374973	Orca installation script need to be modified for solaris building.
132		TBS	enh	Low	354433	Add feature to notify user when a new version is available
133		TBS	nor	Nor	353446	[blocked] Orca not correctly reporting key values in gconf-editor
134	Rich/Close	TBS	min	Low	347959	Graphical smileys in Gaim chatroom cause follow text to not get read immediately
135	Willie	TBS	enh	Nor	349394	Speech Dispatcher Backend
136	Rich/Close	TBS	enh	Nor	326528	Ability to suppress debug trace per module.
999	Rich	TBS	enh	Nor	412359	Better integration with bug buddy.
999		TBS	nor	Nor	415812	[blocked] Orca sometimes provides incorrect information regarding table headers
999		TBS	nor	Nor	413990	[blocked] orca should not speak table over and over again when tabbing through a web page
999		TBS	nor	Nor	412332	[blocked] Orca stops speaking the gnome-panel Application menu entries after I terminate Firefox 3
999		TBS	nor	Nor	414762	[blocked] Control Home/End, Up/Down Arrow don't always work in Firefox
999		TBS	nor	Nor	419138	[blocked] In planner, toggle button on end of "Ribbon" doesn't have accessible name/description
999		TBS	maj	Nor	412677	[blocked] Navigation to links with { overflow:hidden } stylesheet results in bad behavior
999		TBS	nor	Nor	416017	[blocked] FF3 and Orca error reading a page footer
999		TBS	nor	Nor	419139	[blocked] Gnome Screen saver password dialog not accessible
999		TBS	nor	Nor	416971	[blocked] Orca does not speak or braille numbers/bullets of list items in Firefox
999		TBS	maj	Nor	412829	[blocked] Cannot identify selected text in Firefox or Thunderbird
999		TBS	nor	Nor	412252	[blocked] OOo Writer crash when using Orca
999		TBS	nor	Nor	413909	[blocked] Orca can no longer provide "smarts" for spell checking in OOo Writer v2.1 (or later)
999	Willie/Close	TBS	enh	Nor	420191	Enabling Orca to work with MBROLA / FreetTTS
999	Willie/Close	TBS	nor	Nor	420126	Learn mode doesn't detect Firefox-specific keys
999	Rich	TBS	enh	Nor	419089	Refactor StarOffice.py script.
999	Lynn	TBS	nor	Nor	412837	Orca needs test code coverage reporting
999	Rich	TBS	nor	Nor	414981	Orca manual pages for 2.18
999	Willie	TBS	nor	Nor	419123	Modified speech settings do not change immediately in preferences dialog
999	Joanie	TBS	enh	Nor	414657	Linked headings should be announced as both heading and link
999	Willie	TBS	nor	Nor	414738	Flat review in Firefox doesn't start at caret position
999	Willie	TBS	enh	Nor	412661	Gecko.py: determine isUselessObject vs. isLayoutOnly relationship
999	Willie	TBS	maj	Nor	415201	Mouse cusor will not change its shape in magnified screen.
999		TBS	nor	Nor	419135	[blocked] Tables with column headers have accessibility issues
999		TBS	nor	Nor	419141	[blocked] When deleting messages in Evolution, Orca initially speaks the wrong tree item
999		TBS	nor	Nor	419137	[blocked] planner Edit Task Properties dialog has broken accessible component hierarchy
999		TBS	nor	Nor	419136	[blocked] Planner toggle button in main window not accessible
999	Lynn	TBS	maj	Nor	415061	regression test results should be repeatable
999	Willie	TBS	enh	Nor	419742	Add it the ability to switch languages.
999	Willie/Joanie	TBS	enh	Nor	414926	Orca should announce the level of headings in Firefox
999		TBS	nor	Nor	419142	[blocked] The accessible name for Evolution mail message header list "checkbox" table cells is not useful
999		TBS	nor	Nor	418287	[blocked] Treat words separated by non-breaking spaces as a single word in OOo
999	Lynn	TBS	nor	Nor	416332	Orca test coverage needs to be extended