## Sheet1
Rank	Who	Target	Sev	Pri	ID	Summary
1	FF METABUG		maj	Hig	404403	Firefox Metabug
2	Joanie	GNOME 2.19.5	enh	Maj	407941	Infer labels for objects in HTML content
3	Joanie		nor	Nor	407663	[blocked] Support the "Find" operation in Firefox better
4	Joanie	GNOME 2.19.2	maj	Hig	423534	structural navigation should not get stuck on slashdot.org
5	Joanie	GNOME 2.19.1	nor	Nor	411261	Some HTML constructs cause Orca to say just "Link" when arrowing up and down by line
6	Mike		maj	Nor	423224	Firefox should not crash while submitting bugs in Bugzilla with Orca running
7	Willie	GNOME 2.19.2	maj	Nor	412677	[blocked] Navigation to links with { overflow:hidden } stylesheet results in bad behavior
8	Willie	GNOME 2.19.2	nor	Nor	423435	Orca is too chatty when loading a page in Firefox
9	Joanie	GNOME 2.19.1	nor	Nor	423198	Orca should not speak "text" repeatedly when moving around in a text entry area on a web page
10	Joanie	GNOME 2.19.2	nor	Nor	413990	[blocked] orca should not speak table over and over again when tabbing through a web page
11			nor	Nor	414762	[blocked] Control Home/End, Up/Down Arrow don't always work in Firefox
12	Joanie	GNOME 2.19.4	nor	Nor	423427	Need to add form field structural navigation in Firefox
13	Joanie	GNOME 2.19.1	nor	Nor	416971	[blocked] Orca does not speak or braille numbers/bullets of list items in Firefox
14	Willie/Joanie	GNOME 2.19.1	enh	Nor	414926	Orca should announce the level of headings in Firefox
15	Joanie		nor	Nor	422924	Add more support for accessing HTML tables in Firefox
16		GNOME 2.19.90	nor	Nor	423348	Support DHTML, AJAX, ARIA in Firefox/Gecko
17	Willie/Solaris		nor	Nor	423354	Keyboard navigation broken on http://www.blindcooltech.com/
18	Rich	GNOME 2.19.90	enh	Nor	400716	[requirement] sayAll should be done by sentences.
19	Willie	GNOME 2.19.1	maj	Nor	412200	Orca L10N / Translation issues
20	Willie	GNOME 2.19.1	nor	Nor	423439	Speech context includes too much information
21	Lynn	GNOME 2.19.1	nor	Nor	412837	Orca needs test code coverage reporting
22	Lynn	GNOME 2.19.1	maj	Nor	415061	regression test results should be repeatable
23	Lynn		nor	Nor	416332	Orca test coverage needs to be extended
24	Lynn	GNOME 2.19.1	nor	Nor	368626	[blocked] Orca accessing tool tips from gnome-panel causes gnome-panel to crash
25	Wilie	GNOME 2.19.1	enh	Nor	398009	Orca should be able to provide tooltip text for an object
26	Lynn	GNOME 2.20!	nor	Nor	368640	[blocked] Orca should present tool tips when they are popped up
27	Lynn	GNOME 2.20!	nor	Nor	354479	[blocked] [requirement] Automatic presentation of "balloon" type messages
28	Rich	GNOME 2.20	nor	Nor	404411	OpenOffice Metabug
29		GNOME 2.20!	min	Nor	356066	[blocked] Items in OOo's Navigator window are not always spoken
30		GNOME 2.20!	enh	Nor	356060	[blocked] Provide access to tree item level and state in OOo Navigator
31		TBS	nor	Nor	413909	[blocked] Orca can no longer provide "smarts" for spell checking in OOo Writer v2.1 (or later)
32		GNOME 2.20!	enh	Nor	363827	[blocked] Insert F should provide access to the style and font name in OOo Writer
33	Mike Spec	GNOME 2.20!	enh	Nor	372965	[blocked] Insert F should provide access to ALL attributes applied to text in OOo Writer
34	Joanie	GNOME 2.20!	enh	Nor	363830	[blocked] Provide feedback in OOo when toggling bold, underline, and italics
35		GNOME 2.20!	enh	Nor	404046	[blocked] Provide feedback in OOo when a command changes attributes
36		GNOME 2.20!	nor	Nor	376517	[blocked] Orca does not report indentation in OOo Writer documents correctly
37		GNOME 2.20!	maj	Nor	361737	[blocked] It is not possible to navigate to form controls using the keyboard in OOo Writer
38		TBS	nor	Nor	412252	[blocked] OOo Writer crash when using Orca
39	Rich	GNOME 2.20	enh	Nor	372273	Add ability to configure app-specific settings via GUI
40	Mike	GNOME 2.20!	enh	Nor	382601	Orca should indicate selected text on the braille display
41	Mike Spec	GNOME 2.20!	enh	Nor	400720	[requirement] Support accurate presentation of text attributes on the braille display
42		TBS	nor	Nor	419139	[blocked] Gnome Screen saver password dialog not accessible
43		GNOME 2.20?	nor	Nor	354466	[requirement] Watched Objects
44		GNOME 2.20?	min	Nor	354468	[requirement] Bookmarked Objects
45			cri	Nor	423323	Thunderbird 3.0-a1 crashes every time I close a message.
46		TBS	nor	Nor	349978	[blocked] Orca does not announce a message change when deleting a message in evolution
47		TBS	nor	Nor	353470	[blocked] Orca does not speak when the last message in the Evolution mail message header summary list is deleted.
48			nor	Nor	423346	Evolution Metabug
49		TBS	nor	Nor	419141	[blocked] When deleting messages in Evolution, Orca initially speaks the wrong tree item
50		TBS	nor	Nor	353458	[blocked] Text selection in Evolution "New Message" text area is not reported.
51			enh	Nor	422487	Ability to jump to the start of the message in Evolution.
52		TBS	nor	Nor	424149	Evolution mail message window inconsistent with item selected in mail header list.
53		TBS	nor	Nor	353434	[blocked] Backspaced characters in the 'subject' and 'to' lines of evolution are not announced.
54		TBS	nor	Nor	401889	[blocked] Orca does not speak backspaced characters in certain dialogs
55		TBS	nor	Nor	342131	[requirement] Implement verbalized links
56	Rich	GNOME 2.20?	enh	Nor	364518	Create a GUI interface to the pronunciation dictionary.
57		GNOME 2.20?	enh	Nor	425563	[blocked] Provide structural navigation of PDF documents
58		TBS	nor	Nor	423436	RealPlayer doesn't seem to work well with Orca
59		TBS	nor	Nor	407658	[blocked] Cannot access status bar information in Gedit
60	Willie	TBS	enh	Nor	419742	Add it the ability to switch languages.
61			nor	Nor	420324	Problems building Access Bridge v1.5.0
62	Willie	TBS	enh	Nor	405759	Distinguish Q and BLOCKQUOTE in (X)HTML content
63	Willie	GNOME 2.20!	nor	Nor	345399	Key echo missing alpha numeric and punctuation keys.
64		TBS	nor	Nor	402835	[blocked] In Firefox 3.0 a submenu of the bookmarks menu cannot be accessed, if speech is activated.
65			enh	Nor	422475	Orca should speak the word deleted if You enter Control-Backspace.
66	Rich	GNOME 2.18!	maj	Hig	404409	Thunderbird Metabug
67	Willie/Rich	TBS	nor	Nor	409728	Orca repeats mouse-selected text numerous times in thunderbird
68	Rich	TBS	enh	Nor	409736	Orca does not announce the beginning of strings pasted into thunderbird
69		TBS	nor	Nor	374537	[blocked] Thunderbird 3.0 checkbox table cells in subscribe dialog do not provide checked/unchecked state
70		TBS	nor	Nor	373135	[blocked] Thunderbird 3.0 add-on dialog buttons not spoken
71		GNOME 2.18!	maj	Hig	354467	Opening URL in Freeloader hangs Orca
72	Willie	GNOME 2.20!	maj	Hig	NO ID	Accessible Installation of Solaris Express
73	Joanie	TBS	nor	Nor	412100	Text selection in Firefox fails when Orca controls the caret
74	Willie	GNOME 2.20!	maj	Hig	404422	Support per-URL Scripts
75	Lynn	TBS	nor	Nor	410088	NetworkManager applet not spoken when network is disconnected
76		GNOME 2.20!	nor	Nor	352163	[blocked] Orca announces incorrect info in Deskbar Applet
77	Rich	TBS	enh	Nor	409731	Orca should speak text selected by the mouse
78	Willie	TBS	nor	Nor	375782	The performance of orca full screen magnification is not good.
79	Willie	TBS	nor	Nor	375396	Orca failed to exit after stopping the full screen mag.
80	Willie	TBS	cri	Nor	399639	Orca crashes and magnifier hangs if user enables the magnifier.
81	Willie	TBS	nor	Nor	403760	Emacspeak speech factory doesn't always shutdown/restart correctly
82		GNOME 2.20!	maj	Hig	408071	[blocked] Flat review of Firefox reveals content from all tabs
83	Willie	TBS	maj	Nor	355525	Orca skipped one line of web content in flatreview mode.
84		GNOME 2.20!	nor	Nor	383120	[blocked] Ekiga conversation message cannot be read by orca
85		TBS	nor	Nor	352086	[blocked] Orca stops speaking items in Evolution's Select a Folder dialog if you start typing
86		TBS	nor	Nor	353468	[blocked] Orca not always reporting expanded state of Evolution mail tree items.
87		GNOME 2.20!	nor	Nor	354782	[blocked] gnome-system-monitor "Resources" tab is inaccessible
88		GNOME 2.20!	nor	Nor	356041	Previous link in desktop helper can not be read by orca.
89		GNOME 2.20!	nor	Nor	356042	[blocked] The labels in File Management Preferences (nautilus-file-management-properties) window were not reported by orca.
90		GNOME 2.20!	nor	Nor	397680	[blocked] OOo Writer Save As Encoded Text throws up a dialog that is not properly spoken
91		GNOME 2.20!	nor	Nor	385828	[blocked] Can not use agenda wizard in OpenOffice.org
92		GNOME 2.20!	nor	Nor	357545	[blocked] Orca does not speak all buttons in openoffice database table creation wizzard
93	Willie	GNOME 2.20?	enh	Nor	400717	Orca should support multi-lingual text.
94	Willie	TBS	enh	Nor	397306	Orca's default synthesis engine choice should take language into account
95	Mike/Joanie Spec	GNOME 2.20	nor	Nor	400728	[requirement] Orca should provide a means to quickly set often-used preferences
96		TBS	nor	Nor	347691	[blocked] In standard print dialog, printer table items not always spoken/displayed
97		GNOME 2.20	nor	Nor	354470	[requirement] Grade 2 Braille
98		GNOME 2.20	enh	Nor	400718	[requirement] Braille: Effective presentation of white space.
99		GNOME 2.20	min	Nor	354471	[requirement] Text selection from braille input device
100	Rich	GNOME 2.20	nor	Nor	376015	[a11y] time-admin time servers table is not accessible.
101		GNOME 2.20	enh	Nor	424528	Script support for gnucash.
102		GNOME 2.20	enh	Nor	424531	Script support for Rhythmbox.
103		GNOME 2.20	enh	Nor	363820	[blocked] Orca should inform the user when text in given cell in Calc is too wide for that column
104	Rich	GNOME 2.20	nor	Nor	397668	Blank lines are not announced as blank lines in gnome-terminal
105		GNOME 2.20?	nor	Nor	400729	[requirement] Orca should provide support for general audio
106		GNOME 2.20?	min	Nor	354474	[requirement] Audio cues when crossing line boundaries
107		GNOME 2.20?	nor	Nor	350742	[blocked] text from text boxes not reported all the time in java applications
108	Lynn	TBS	nor	Nor	407704	jedit does not speak or braille text in composition area
109		GNOME 2.20?	enh	Nor	424529	Script support for Planner.
110	Rich	GNOME 2.20?	enh	Nor	376515	Add GUI support for the new customizable text-attribute feature
111		GNOME 2.20?	enh	Nor	424522	Script support for a bittorrent client.
112		GNOME 2.20?	enh	Nor	363804	Add ability to turn off coordinate announcement when navigating in Calc
113	Mike Spec	GNOME 2.20?	min	Nor	354459	[requirement] Verbalized caps
114		GNOME 2.20?	enh	Nor	363793	Add the ability to change the color of the flat review rectangle
115		GNOME 2.20?	min	Nor	354464	[requirement] Jump to well-known object
116	Ask List	TBS	enh	Nor	412656	Refactor speech generators to provide ACSS per string
117		GNOME 2.20?	enh	Nor	424525	Script support for gnome-blogger.
118		GNOME 2.20?	nor	Nor	364772	[blocked] Orca can not detect miss-spelled words on the fly in Openoffice
119		GNOME 2.20?	nor	Nor	371637	[blocked] Orca repeats "Location:" info repeatedly in Nautilus File Browser Dialog
120		GNOME 2.20?	nor	Nor	365284	[blocked] Evolution's account wizard Welcome message will not be reported by orca
121		GNOME 2.20?	enh	Nor	424524	Script support for gftp.
122	Rich	GNOME 2.20?	nor	Nor	395146	Crash at start
123		TBS	enh	Low	373387	Users should be able to lock/unlock the "Lock" modifier even if Caps Lock is the Orca modifier
124	Joanie	GNOME 2.20?	enh	Low	387556	Arrowing past last character at end of line in Orca results in no speech
125	Rich	TBS	nor	Nor	400711	Script support for Planner.
126		TBS	enh	Nor	400732	[requirement] Toggle between logical and screen braille presentations.
127	Willie/Rich	TBS	nor	Low	373078	Unable to change voice in application specif settings file.
128		TBS	enh	Nor	356068	[blocked] Provide a command for identifying the default button within a dialog
129		TBS	min	Nor	354462	[requirement] SayAll of dialogs (versus just a single text area)
130	Willie/Close	TBS	enh	Low	319659	Automatic documentation for keybinds script.
131		TBS	enh	Low	319752	Orca should support multiline braille displays
132		TBS	nor	Nor	364765	[blocked] Escaping out of Wizards submenu in OOo Writer causes Orca to report "Format menu"
133		TBS	nor	Nor	408430	COMM_FAILURE when running simple Gtk application
134		TBS	enh	Nor	407647	[blocked] Indicate the tree level of items in the Gaim (post 2.0 beta 3.1) buddy list
135		TBS	nor	Nor	355524	[blocked] Flatreview doesn't work in gnome-about panel.
136		TBS	blo	Nor	362627	[blocked] Thunderbird folder properties: no relationship between page tabs and page contents
137		TBS	enh	Low	354433	Add feature to notify user when a new version is available
138		TBS	nor	Nor	353446	[blocked] Orca not correctly reporting key values in gconf-editor
139	Willie	TBS	enh	Nor	349394	Speech Dispatcher Backend
999			nor	Nor	381455	[blocked] Thunderbird does not present labels around dialog text entries
999	Rich	TBS	enh	Nor	412359	Better integration with bug buddy.
999	Willie	TBS	enh	Nor	412661	Gecko.py: determine isUselessObject vs. isLayoutOnly relationship
999		TBS	maj	Nor	412829	[blocked] Cannot identify selected text in Firefox or Thunderbird
999	Joanie	TBS	enh	Nor	414657	Linked headings should be announced as both heading and link
999	Willie	TBS	nor	Nor	414738	Flat review in Firefox doesn't start at caret position
999	Willie	TBS	maj	Nor	415201	Mouse cusor will not change its shape in magnified screen.
999		TBS	nor	Nor	415812	[blocked] Orca sometimes provides incorrect information regarding table headers
999		TBS	nor	Nor	416017	[blocked] FF3 and Orca error reading a page footer
999		TBS	nor	Nor	418287	[blocked] Treat words separated by non-breaking spaces as a single word in OOo
999	Willie	TBS	nor	Nor	419123	Modified speech settings do not change immediately in preferences dialog
999		TBS	nor	Nor	419135	[blocked] Tables with column headers have accessibility issues
999		TBS	nor	Nor	419136	[blocked] Planner toggle button in main window not accessible
999		TBS	nor	Nor	419137	[blocked] planner Edit Task Properties dialog has broken accessible component hierarchy
999		TBS	nor	Nor	419138	[blocked] In planner, toggle button on end of "Ribbon" doesn't have accessible name/description
999		TBS	nor	Nor	419142	[blocked] The accessible name for Evolution mail message header list "checkbox" table cells is not useful
999			enh	Nor	420540	Firefox keyboard control wish list.
999		TBS	enh	Nor	423440	Permit reloading of scripts while Orca is running
999		GNOME 2.20?	enh	Nor	425498	[pending] Option to allow Orca to quit without confirmation when user presses Insert-q