## Sheet1
Rank	Who	Target	Sev	Pri	ID	Summary
1	Joanie	GNOME 2.18!	maj	Hig	404403	Firefox Metabug
2	Lynn	TBS	maj	Nor	415061	regression test results should be repeatable
3	Lynn	TBS	nor	Nor	416332	Orca test coverage needs to be extended
4			nor	Nor	423346	Evolution Metabug
5	Rich	GNOME 2.20!	enh	Nor	395548	Refactor calls to util.py as calls from delegates in default.py
6	Rich	GNOME 2.20!	enh	Low	402494	For statement refactoring.
7	Rich	TBS	enh	Nor	419089	Refactor StarOffice.py script.
8			enh	Nor	423011	Need to refactor where_am_I.py
9	Willie	GNOME 2.20!	maj	Nor	412200	Orca L10N / Translation issues
10	Willie	GNOME 2.20!	nor	Nor	345399	Key echo missing alpha numeric and punctuation keys.
11	Rich	GNOME 2.19.0	enh	Nor	350674	make orca announce when a new folder is opened and announce number of items
12	Willie/Rich	TBS	nor	Nor	342131	[requirement] Implement verbalized links
13		TBS	nor	Nor	402835	[blocked] In Firefox 3.0 a submenu of the bookmarks menu cannot be accessed, if speech is activated.
14	Rich	GNOME 2.18!	maj	Hig	404409	Thunderbird Metabug
15	Willie/Rich	TBS	nor	Nor	409728	Orca repeats mouse-selected text numerous times in thunderbird
16	Rich	TBS	enh	Nor	409736	Orca does not announce the beginning of strings pasted into thunderbird
17		TBS	nor	Nor	374537	[blocked] Thunderbird 3.0 checkbox table cells in subscribe dialog do not provide checked/unchecked state
18		TBS	nor	Nor	373135	[blocked] Thunderbird 3.0 add-on dialog buttons not spoken
19		GNOME 2.18!	maj	Hig	354467	Opening URL in Freeloader hangs Orca
20	Willie	GNOME 2.18!	enh	Nor	408670	Braille and speech don't track well in text entry areas in Firefox and Thunderbird
21	Joanie	GNOME 2.18!	enh	Nor	407948	{Shift+}o and {Shift+}h do not work reliably in Firefox
22	Ask List	TBS	enh	Nor	412656	Refactor speech generators to provide ACSS per string
23	Rich	TBS	min	Nor	413109	HIG violations
24	Rich	TBS	enh	Nor	410302	Better support for gnome-mud application
25	Joanie	GNOME 2.19.1	enh	Nor	407941	Infer labels for objects in HTML content
26	Willie	GNOME 2.20!	maj	Hig	NO ID	Accessible Installation of Solaris Express
27	Joanie	TBS	nor	Nor	407663	Support the "Find" operation in Firefox better
28	Willie/Joanie	TBS	nor	Nor	411261	Some HTML constructs cause Orca to say just "Link" when arrowing up and down by line
29	Joanie	TBS	nor	Nor	412100	Text selection in Firefox fails when Orca controls the caret
30	Willie	GNOME 2.20!	maj	Hig	404422	Support per-URL Scripts
31		TBS	nor	Nor	353434	[blocked] Backspaced characters in the 'subject' and 'to' lines of evolution are not announced.
32		TBS	nor	Nor	401889	[blocked] Orca does not speak backspaced characters in certain dialogs
33		GNOME 2.20!	nor	Nor	354479	[blocked] [requirement] Automatic presentation of "balloon" type messages
34	Lynn	TBS	nor	Nor	410088	NetworkManager applet not spoken when network is disconnected
35		GNOME 2.20!	nor	Nor	352163	[blocked] Orca announces incorrect info in Deskbar Applet
36		GNOME 2.20!	enh	Nor	363827	[blocked] Insert F should provide access to the style and font name in OOo Writer
37		GNOME 2.20!	enh	Nor	372965	[blocked] Insert F should provide access to ALL attributes applied to text in OOo Writer
38		GNOME 2.20!	enh	Nor	363830	[blocked] Provide feedback in OOo when toggling bold, underline, and italics
39		GNOME 2.20!	enh	Nor	404046	[blocked] Provide feedback in OOo when a command changes attributes
40		GNOME 2.20!	nor	Nor	376517	[blocked] Orca does not report indentation in OOo Writer documents correctly
41		GNOME 2.20!	maj	Nor	361737	[blocked] It is not possible to navigate to form controls using the keyboard in OOo Writer
42	Rich/Close	GNOME 2.20!	nor	Nor	400712	Orca doesn't provide compelling access to ooimpress
43		GNOME 2.20!	nor	Nor	368626	[blocked] Orca accessing tool tips from gnome-panel causes gnome-panel to crash
44		GNOME 2.20!	nor	Nor	368640	[blocked] Orca should present tool tips when they are popped up
45	Lynn	GNOME 2.20!	enh	Nor	398009	Orca should be able to provide tooltip text for an object
46	Mike	GNOME 2.20!	enh	Nor	382601	Orca should indicate selected text on the braille display
47	Rich	TBS	enh	Nor	409731	Orca should speak text selected by the mouse
48	Mike Spec	GNOME 2.20!	enh	Nor	400720	[requirement] Support accurate presentation of text attributes on the braille display
49	Rich	TBS	nor	Nor	402192	Orca does not speak text that is pasted in by middle mouse click.
50	Willie	TBS	nor	Nor	375782	The performance of orca full screen magnification is not good.
51	Willie	TBS	nor	Nor	375396	Orca failed to exit after stopping the full screen mag.
52	Willie	TBS	cri	Nor	399639	Orca crashes and magnifier hangs if user enables the magnifier.
53	Willie	TBS	nor	Nor	403760	Emacspeak speech factory doesn't always shutdown/restart correctly
54	Mike Spec	GNOME 2.20!	enh	Nor	400716	[requirement] sayAll should be done by sentences.
55		GNOME 2.20!	maj	Hig	408071	[blocked] Flat review of Firefox reveals content from all tabs
56	Willie	TBS	maj	Nor	355525	Orca skipped one line of web content in flatreview mode.
57		GNOME 2.20!	nor	Nor	383120	[blocked] Ekiga conversation message cannot be read by orca
58		TBS	nor	Nor	353458	[blocked] Text selection in Evolution "New Message" text area is not reported.
59		TBS	nor	Nor	352086	[blocked] Orca stops speaking items in Evolution's Select a Folder dialog if you start typing
60		TBS	nor	Nor	353468	[blocked] Orca not always reporting expanded state of Evolution mail tree items.
61		TBS	nor	Nor	353470	[blocked] Orca does not speak when the last message in the Evolution mail message header summary list is deleted.
62		TBS	nor	Nor	349978	[blocked] Orca does not announce a message change when deleting a message in evolution
63		GNOME 2.20!	nor	Nor	354782	[blocked] gnome-system-monitor "Resources" tab is inaccessible
64		GNOME 2.20!	nor	Nor	356041	Previous link in desktop helper can not be read by orca.
65		GNOME 2.20!	nor	Nor	356042	[blocked] The labels in File Management Preferences (nautilus-file-management-properties) window were not reported by orca.
66		GNOME 2.20!	nor	Nor	397680	[blocked] OOo Writer Save As Encoded Text throws up a dialog that is not properly spoken
67		GNOME 2.20!	nor	Nor	385828	[blocked] Can not use agenda wizard in OpenOffice.org
68		TBS	nor	Nor	407658	[blocked] Cannot access status bar information in Gedit
69		GNOME 2.20!	nor	Nor	357545	[blocked] Orca does not speak all buttons in openoffice database table creation wizzard
70		GNOME 2.20!	min	Nor	356066	[blocked] Items in OOo's Navigator window are not always spoken
71		GNOME 2.20!	enh	Nor	356060	[blocked] Provide access to tree item level and state in OOo Navigator
72	Willie	GNOME 2.20?	enh	Nor	400717	Orca should support multi-lingual text.
73	Willie	TBS	enh	Nor	397306	Orca's default synthesis engine choice should take language into account
74	Mike/Joanie Spec	GNOME 2.20	nor	Nor	400728	[requirement] Orca should provide a means to quickly set often-used preferences
75		TBS	nor	Nor	347691	[blocked] In standard print dialog, printer table items not always spoken/displayed
76		GNOME 2.20	nor	Nor	354470	[requirement] Grade 2 Braille
77		GNOME 2.20	enh	Nor	400718	[requirement] Braille: Effective presentation of white space.
78		GNOME 2.20	min	Nor	354471	[requirement] Text selection from braille input device
79	Rich	GNOME 2.20	enh	Nor	372273	Add ability to configure app-specific settings via GUI
80	Rich	GNOME 2.20	nor	Nor	376015	[a11y] time-admin time servers table is not accessible.
81	Rich/OPEN	GNOME 2.20	nor	Nor	NO ID	Support for gnucash
82	Rich/OPEN	GNOME 2.20	nor	Nor	NO ID	Support for Rhythmbox
83		GNOME 2.20	enh	Nor	363820	[blocked] Orca should inform the user when text in given cell in Calc is too wide for that column
84	Rich	GNOME 2.20	nor	Nor	397668	Blank lines are not announced as blank lines in gnome-terminal
85		GNOME 2.20?	nor	Nor	400729	[requirement] Orca should provide support for general audio
86		GNOME 2.20?	min	Nor	354474	[requirement] Audio cues when crossing line boundaries
87		GNOME 2.20?	nor	Nor	350742	[blocked] text from text boxes not reported all the time in java applications
88	Lynn	TBS	nor	Nor	407704	jedit does not speak or braille text in composition area
89	Rich/OPEN	GNOME 2.20?	nor	Nor	NO ID	Support for Planner
90	Rich	GNOME 2.20?	enh	Nor	376515	Add GUI support for the new customizable text-attribute feature
91	Rich/OPEN	GNOME 2.20?	nor	Nor	NO ID	Support for a bittorrent client.
92		GNOME 2.20?	enh	Nor	363804	Add ability to turn off coordinate announcement when navigating in Calc
93	Rich	GNOME 2.20?	enh	Nor	364518	Create a GUI interface to the pronunciation dictionary.
94	Willie	TBS	enh	Nor	405759	Distinguish Q and BLOCKQUOTE in (X)HTML content
95	Mike Spec	GNOME 2.20?	min	Nor	354459	[requirement] Verbalized caps
96		GNOME 2.20?	enh	Nor	363793	Add the ability to change the color of the flat review rectangle
97		GNOME 2.20?	min	Nor	354464	[requirement] Jump to well-known object
98		GNOME 2.20?	nor	Nor	354466	[requirement] Watched Objects
99		GNOME 2.20?	min	Nor	354468	[requirement] Bookmarked Objects
100		TBS	enh	Nor	400715	[requirement] Extend the Find command for HTML web content.
101	Rich/OPEN	GNOME 2.20?	nor	Nor	NO ID	Support for gnome-blogger
102		GNOME 2.20?	nor	Nor	364772	[blocked] Orca can not detect miss-spelled words on the fly in Openoffice
103		GNOME 2.20?	nor	Nor	371637	[blocked] Orca repeats "Location:" info repeatedly in Nautilus File Browser Dialog
104		GNOME 2.20?	nor	Nor	365284	[blocked] Evolution's account wizard Welcome message will not be reported by orca
105	Rich/OPEN	GNOME 2.20?	nor	Nor	NO ID	Support for gftp
106	Rich	GNOME 2.20?	nor	Nor	395146	Crash at start
107		TBS	enh	Low	373387	Users should be able to lock/unlock the "Lock" modifier even if Caps Lock is the Orca modifier
108	Joanie	GNOME 2.20?	enh	Low	387556	Arrowing past last character at end of line in Orca results in no speech
109	Rich	TBS	nor	Nor	400711	Month view is inaccessible in Evolution calendar.
110		TBS	enh	Nor	400732	[requirement] Toggle between logical and screen braille presentations.
111	Willie/Rich	TBS	nor	Low	373078	Unable to change voice in application specif settings file.
112		TBS	enh	Nor	356068	[blocked] Provide a command for identifying the default button within a dialog
113		TBS	min	Nor	354462	[requirement] SayAll of dialogs (versus just a single text area)
114	Willie/Close	TBS	enh	Low	319659	Automatic documentation for keybinds script.
116		TBS	enh	Low	319752	Orca should support multiline braille displays
118		TBS	nor	Nor	364765	[blocked] Escaping out of Wizards submenu in OOo Writer causes Orca to report "Format menu"
119	Rich	GNOME 2.20	nor	Nor	404411	OpenOffice Metabug
120		TBS	nor	Nor	408430	COMM_FAILURE when running simple Gtk application
125		TBS	enh	Nor	407647	[blocked] Indicate the tree level of items in the Gaim (post 2.0 beta 3.1) buddy list
126		TBS	nor	Nor	355524	[blocked] Flatreview doesn't work in gnome-about panel.
128		TBS	blo	Nor	362627	[blocked] Thunderbird folder properties: no relationship between page tabs and page contents
132		TBS	enh	Low	354433	Add feature to notify user when a new version is available
133		TBS	nor	Nor	353446	[blocked] Orca not correctly reporting key values in gconf-editor
135	Willie	TBS	enh	Nor	349394	Speech Dispatcher Backend
999			nor	Nor	381455	[blocked] Thunderbird does not present labels around dialog text entries
999		TBS	nor	Nor	412252	[blocked] OOo Writer crash when using Orca
999		TBS	nor	Nor	412332	[blocked] Orca stops speaking the gnome-panel Application menu entries after I terminate Firefox 3
999	Rich	TBS	enh	Nor	412359	Better integration with bug buddy.
999	Willie	TBS	enh	Nor	412661	Gecko.py: determine isUselessObject vs. isLayoutOnly relationship
999		TBS	maj	Nor	412677	[blocked] Navigation to links with { overflow:hidden } stylesheet results in bad behavior
999		TBS	maj	Nor	412829	[blocked] Cannot identify selected text in Firefox or Thunderbird
999	Lynn	TBS	nor	Nor	412837	Orca needs test code coverage reporting
999		TBS	nor	Nor	413909	[blocked] Orca can no longer provide "smarts" for spell checking in OOo Writer v2.1 (or later)
999		TBS	nor	Nor	413990	[blocked] orca should not speak table over and over again when tabbing through a web page
999	Joanie	TBS	enh	Nor	414657	Linked headings should be announced as both heading and link
999	Willie	TBS	nor	Nor	414738	Flat review in Firefox doesn't start at caret position
999		TBS	nor	Nor	414762	[blocked] Control Home/End, Up/Down Arrow don't always work in Firefox
999	Willie/Joanie	TBS	enh	Nor	414926	Orca should announce the level of headings in Firefox
999	Rich	TBS	nor	Nor	414981	Orca manual pages for 2.18
999	Willie	TBS	maj	Nor	415201	Mouse cusor will not change its shape in magnified screen.
999		TBS	nor	Nor	415812	[blocked] Orca sometimes provides incorrect information regarding table headers
999		TBS	nor	Nor	416017	[blocked] FF3 and Orca error reading a page footer
999		TBS	nor	Nor	416971	[blocked] Orca does not speak or braille numbers/bullets of list items in Firefox
999		TBS	nor	Nor	418287	[blocked] Treat words separated by non-breaking spaces as a single word in OOo
999	Willie	TBS	nor	Nor	419123	Modified speech settings do not change immediately in preferences dialog
999		TBS	nor	Nor	419135	[blocked] Tables with column headers have accessibility issues
999		TBS	nor	Nor	419136	[blocked] Planner toggle button in main window not accessible
999		TBS	nor	Nor	419137	[blocked] planner Edit Task Properties dialog has broken accessible component hierarchy
999		TBS	nor	Nor	419138	[blocked] In planner, toggle button on end of "Ribbon" doesn't have accessible name/description
999		TBS	nor	Nor	419139	[blocked] Gnome Screen saver password dialog not accessible
999		TBS	nor	Nor	419141	[blocked] When deleting messages in Evolution, Orca initially speaks the wrong tree item
999		TBS	nor	Nor	419142	[blocked] The accessible name for Evolution mail message header list "checkbox" table cells is not useful
999	Willie	TBS	enh	Nor	419742	Add it the ability to switch languages.
999			nor	Nor	420324	Problems building Access Bridge v1.5.0
999			enh	Nor	420540	Firefox keyboard control wish list.
999			enh	Nor	422475	Orca should speak the word deleted if You enter Control-Backspace.
999			enh	Nor	422487	Ability to jump to the start of the message in Evolution.
999			nor	Nor	422924	Add more support for accessing HTML tables in Firefox
999			nor	Nor	423198	Orca should not speak "text" repeatedly when moving around in a text entry area on a web page
999			nor	Nor	423214	Need to add level-specific heading navigation in Firefox
999			maj	Nor	423224	Firefox should not crash while submitting bugs in Bugzilla with Orca running
999			cri	Nor	423323	Thunderbird 3.0-a1 crashes every time I close a message.
999			nor	Nor	423348	Support DHTML, AJAX, ARIA in Firefox/Gecko
999		TBS	nor	Nor	423354	Keyboard navigation broken on http://www.blindcooltech.com/