## Sheet1
Rank	Who	Target	ID	Sev	Pri	Summary
0.5	Wilie	GNOME 2.19.2	432685	nor	Nor	Using brltty can consume all the CPU
1	FF METABUG		404403	maj	Hig	Firefox Metabug
2	Joanie	GNOME 2.19.5	407941	maj	Nor	Infer labels for objects in HTML content
3	Joanie		407663	nor	Nor	[blocked] Support the "Find" operation in Firefox better
4	Joanie	GNOME 2.19.2	423534	maj	Hig	[blocked] structural navigation should not get stuck on slashdot.org
5	Joanie	GNOME 2.19.1	411261	nor	Nor	Some HTML constructs cause Orca to say just "Link" when arrowing up and down by line
7	Willie	GNOME 2.19.2	412677	maj	Nor	[blocked] Navigation to links with { overflow:hidden } stylesheet results in bad behavior
8	Willie	GNOME 2.19.2	423435	nor	Nor	Orca is too chatty when loading a page in Firefox
10			414762	nor	Nor	[blocked] Control Home/End, Up/Down Arrow don't always work in Firefox
11	Joanie	GNOME 2.19.4	423427	nor	Nor	Need to add form field structural navigation in Firefox
12	Joanie	GNOME 2.19.1	416971	nor	Nor	[blocked] Orca does not speak or braille numbers/bullets of list items in Firefox
13	Joanie		422924	nor	Nor	[blocked] Add more support for accessing HTML tables in Firefox
14	Willie	GNOME 2.19.90	423348	nor	Nor	Support DHTML, AJAX, ARIA in Firefox/Gecko
15	Willie/Solaris		423354	nor	Nor	Keyboard navigation broken on http://www.blindcooltech.com/
16	Joanie	TBS	428025	nor	Nor	[pending] Links should not be spoken twice when down arrowing in firefox
17	Joanie	TBS	428114	nor	Nor	Orca sometimes misidentifies combo box contents as the name in Firefox
18	Joanie	TBS	414657	enh	Nor	Linked headings should be announced as both heading and link
19	Willie	TBS	414738	nor	Nor	Flat review in Firefox doesn't start at caret position
21	Joanie	TBS	426360	nor	Nor	SayAll is broken in Firefox
22	Willie	TBS	416017	nor	Nor	[blocked] FF3 and Orca error reading a page footer
23	Rich	GNOME 2.19.90	400716	enh	Nor	[pending] sayAll should be done by sentences.
24	Willie	GNOME 2.19.1	412200	maj	Nor	Orca L10N / Translation issues
26	Lynn	GNOME 2.19.1	412837	nor	Nor	Orca needs test code coverage reporting
27	Lynn	GNOME 2.19.1	415061	maj	Nor	regression test results should be repeatable
28	Lynn		416332	nor	Nor	Orca test coverage needs to be extended
29	Lynn	GNOME 2.20!	368640	enh	Nor	Allow user to optionally ignore or be notified of tool tips
30	Lynn	GNOME 2.20!	354479	nor	Nor	[blocked] [requirement] Automatic presentation of "balloon" type messages
30.1	Lynn		420324	nor	Nor	Problems building Access Bridge v1.5.0
30.5		TBS	430278	nor	Nor	[pending] The Where_Am_I script does not work in most applications.
31	Rich	GNOME 2.20	404411	nor	Nor	OpenOffice Metabug
32	Rich	GNOME 2.20!	356066	min	Nor	[blocked] Items in OOo's Navigator window are not always spoken
33	Rich	GNOME 2.20!	356060	enh	Nor	[blocked] Provide access to tree item level and state in OOo Navigator
34	Rich	TBS	413909	nor	Nor	[blocked] Orca can no longer provide "smarts" for spell checking in OOo Writer v2.1 (or later)
35	Rich	GNOME 2.20!	363827	enh	Nor	[blocked] Insert F should provide access to the style and font name in OOo Writer
36	Mike Spec	GNOME 2.20!	372965	enh	Nor	[blocked] Insert F should provide access to ALL attributes applied to text in OOo Writer
37	Joanie	GNOME 2.20!	363830	enh	Nor	[blocked] Provide feedback in OOo when toggling bold, underline, and italics
38	Rich	GNOME 2.20!	404046	enh	Nor	[blocked] Provide feedback in OOo when a command changes attributes
39	Rich	GNOME 2.20!	376517	nor	Nor	[blocked] Orca does not report indentation in OOo Writer documents correctly
40	Rich	GNOME 2.20!	361737	maj	Nor	[blocked] It is not possible to navigate to form controls using the keyboard in OOo Writer
41	Rich	TBS	412252	nor	Nor	[blocked] OOo Writer crash when using Orca
42	Rich	TBS	429390	nor	Nor	Braille stays on current line after pressing return at end of line in OOo Writer
43	Rich	TBS	426010	enh	Nor	Implement verbalized links in OOo
44		GNOME 2.20?	364772	nor	Nor	[blocked] Orca can not detect miss-spelled words on the fly in Openoffice
44.5		TBS	431030	maj	Nor	[blocked] Cannot use keyboard to navigate gnome-panel notification area
45	Rich	GNOME 2.20	372273	enh	Nor	Add ability to configure app-specific settings via GUI
45.1	Rich	GNOME 2.19.2	433146	enh	Nor	Add ability to configure app-unique settings via GUI
46	Mike	GNOME 2.20!	382601	enh	Nor	Orca should indicate selected text on the braille display
47	Mike Spec	GNOME 2.20!	400720	enh	Nor	[requirement] Support accurate presentation of text attributes on the braille display
48		TBS	419139	nor	Nor	[blocked] Gnome Screen saver password dialog not accessible
49	Rich	GNOME 2.20?	354466	nor	Nor	[requirement] Watched Objects
50	Rich	GNOME 2.20?	354468	min	Nor	[requirement] Bookmarked Objects
50.5		TBS	430402	nor	Nor	[blocked] Orca unable to speak last character of each "sentence" when doing a sayAll in OOo Writer
51			423323	cri	Nor	[blocked] Thunderbird 3.0-a1 crashes every time I close a message.
52			423346	nor	Nor	Evolution Metabug
53		TBS	349978	nor	Nor	[blocked] Orca does not announce a message change when deleting a message in evolution
54		TBS	353470	nor	Nor	[blocked] Orca does not speak when the last message in the Evolution mail message header summary list is deleted.
57		TBS	353458	nor	Nor	[pending] Text selection in Evolution "New Message" text area is not reported.
58			422487	enh	Nor	[blocked] Ability to jump to the start of the message in Evolution.
59		TBS	424149	nor	Nor	Evolution mail message window inconsistent with item selected in mail header list.
60		TBS	353434	nor	Nor	[blocked] Backspaced characters in the 'subject' and 'to' lines of evolution are not announced.
61		TBS	401889	nor	Nor	[blocked] Orca does not speak backspaced characters in certain dialogs
61.5	Willie	TBS	419742	enh	Nor	Add it the ability to switch languages.
62	Rich	GNOME 2.20?	364518	enh	Nor	Create a GUI interface to the pronunciation dictionary.
63	Joanie	GNOME 2.20?	425563	enh	Nor	[blocked] Provide structural navigation of PDF documents
64		TBS	423436	nor	Nor	RealPlayer doesn't seem to work well with Orca
65		TBS	407658	nor	Nor	[blocked] Cannot access status bar information in Gedit
68	Willie	TBS	405759	enh	Nor	Distinguish Q and BLOCKQUOTE in (X)HTML content
69	Willie	GNOME 2.20!	345399	nor	Nor	Key echo missing alpha numeric and punctuation keys.
70		TBS	402835	nor	Nor	[blocked] In Firefox 3.0 a submenu of the bookmarks menu cannot be accessed, if speech is activated.
71	Rich		422475	enh	Nor	Orca should speak the word deleted if You enter Control-Backspace.
72	Rich	GNOME 2.18!	404409	nor	Hig	Thunderbird Metabug
73	Willie/Rich	TBS	409728	nor	Nor	Orca repeats mouse-selected text numerous times in thunderbird
74	Rich	TBS	409736	enh	Nor	[blocked] Orca does not announce the beginning of strings pasted into thunderbird
75		TBS	374537	nor	Nor	[blocked] Thunderbird 3.0 checkbox table cells in subscribe dialog do not provide checked/unchecked state
76		TBS	373135	nor	Nor	[blocked] Thunderbird 3.0 add-on dialog buttons not spoken
77		GNOME 2.18!	354467	maj	Hig	Opening URL in Freeloader hangs Orca
78	Willie	GNOME 2.20!	NO ID	maj	Hig	Accessible Installation of Solaris Express
79	Joanie	TBS	412100	nor	Nor	Text selection in Firefox fails when Orca controls the caret
80	Willie	GNOME 2.20!	404422	nor	Nor	Support per-URL Scripts
81	Lynn	TBS	410088	nor	Nor	NetworkManager applet not spoken when network is disconnected
82		GNOME 2.20!	352163	nor	Nor	[blocked] Orca announces incorrect info in Deskbar Applet
83	Rich	TBS	409731	enh	Nor	Orca should speak text selected by the mouse
84	Willie	TBS	375782	nor	Nor	The performance of orca full screen magnification is not good.
85	Willie	TBS	375396	nor	Nor	Orca failed to exit after stopping the full screen mag.
86	Willie	TBS	399639	cri	Nor	Orca crashes and magnifier hangs if user enables the magnifier.
87	Willie	TBS	403760	nor	Nor	Emacspeak speech factory doesn't always shutdown/restart correctly
88	Willie	TBS	355525	maj	Nor	Orca skipped one line of web content in flatreview mode.
89		GNOME 2.20!	383120	nor	Nor	[blocked] Ekiga conversation message cannot be read by orca
90		GNOME 2.20!	354782	nor	Nor	[blocked] gnome-system-monitor "Resources" tab is inaccessible
91		GNOME 2.20!	356041	nor	Nor	Previous link in desktop helper can not be read by orca.
92		GNOME 2.20!	356042	nor	Nor	[blocked] The labels in File Management Preferences (nautilus-file-management-properties) window were not reported by orca.
93		GNOME 2.20!	397680	nor	Nor	[blocked] OOo Writer Save As Encoded Text throws up a dialog that is not properly spoken
94		GNOME 2.20!	385828	nor	Nor	[blocked] Can not use agenda wizard in OpenOffice.org
95		GNOME 2.20!	357545	nor	Nor	[blocked] Orca does not speak all buttons in openoffice database table creation wizzard
96	Willie	GNOME 2.20?	400717	enh	Nor	Orca should support multi-lingual text.
97	Willie	TBS	397306	enh	Nor	Orca's default synthesis engine choice should take language into account
98	Mike/Joanie Spec	GNOME 2.20	400728	nor	Nor	[requirement] Orca should provide a means to quickly set often-used preferences
99		TBS	347691	nor	Nor	[blocked] In standard print dialog, printer table items not always spoken/displayed
100		GNOME 2.20	354470	nor	Nor	[requirement] Grade 2 Braille
101		GNOME 2.20	400718	enh	Nor	[requirement] Braille: Effective presentation of white space.
102		GNOME 2.20	354471	min	Nor	[requirement] Text selection from braille input device
103	Rich	GNOME 2.20	376015	nor	Nor	[a11y] time-admin time servers table is not accessible.
104		GNOME 2.20	424528	enh	Nor	Script support for gnucash.
105		GNOME 2.20	424531	enh	Nor	Script support for Rhythmbox.
106		GNOME 2.20	363820	enh	Nor	[blocked] Orca should inform the user when text in given cell in Calc is too wide for that column
107	Rich	GNOME 2.20	397668	nor	Nor	Blank lines are not announced as blank lines in gnome-terminal
108		GNOME 2.20?	400729	nor	Nor	[requirement] Orca should provide support for general audio
109		GNOME 2.20?	354474	min	Nor	[requirement] Audio cues when crossing line boundaries
110		GNOME 2.20?	350742	nor	Nor	[blocked] text from text boxes not reported all the time in java applications
111	Lynn	TBS	407704	nor	Nor	jedit does not speak or braille text in composition area
112		GNOME 2.20?	424529	enh	Nor	Script support for Planner.
113	Rich	GNOME 2.20?	376515	enh	Nor	Add GUI support for the new customizable text-attribute feature
114		GNOME 2.20?	424522	enh	Nor	Script support for a bittorrent client.
115		GNOME 2.20?	363804	enh	Nor	Add ability to turn off coordinate announcement when navigating in Calc
116	Mike Spec	GNOME 2.20?	354459	min	Nor	[requirement] Verbalized caps
117		GNOME 2.20?	363793	enh	Nor	Add the ability to change the color of the flat review rectangle
118	Ask List	TBS	412656	enh	Nor	Refactor speech generators to provide ACSS per string
119		GNOME 2.20?	424525	enh	Nor	Script support for gnome-blogger.
120		GNOME 2.20?	371637	nor	Nor	[blocked] Orca repeats "Location:" info repeatedly in Nautilus File Browser Dialog
121		GNOME 2.20?	365284	nor	Nor	[blocked] Evolution's account wizard Welcome message will not be reported by orca
122		GNOME 2.20?	424524	enh	Nor	Script support for gftp.
123	Rich	GNOME 2.20?	395146	nor	Nor	Crash at start
124		TBS	373387	enh	Low	Users should be able to lock/unlock the "Lock" modifier even if Caps Lock is the Orca modifier
125	Joanie	GNOME 2.20?	387556	enh	Low	Arrowing past last character at end of line in Orca results in no speech
126	Rich	TBS	400711	nor	Nor	Month view is inaccessible in Evolution calendar.
127		TBS	400732	enh	Nor	[requirement] Toggle between logical and screen braille presentations.
128	Willie/Rich	TBS	373078	min	Low	Unable to change voice in application specif settings file.
129		TBS	356068	enh	Nor	[blocked] Provide a command for identifying the default button within a dialog
130		TBS	354462	min	Nor	[requirement] SayAll of dialogs (versus just a single text area)
131		TBS	319659	enh	Low	Automatic documentation for keybinds script.
132		TBS	319752	enh	Low	Orca should support multiline braille displays
133		TBS	364765	nor	Nor	[blocked] Escaping out of Wizards submenu in OOo Writer causes Orca to report "Format menu"
134		TBS	408430	nor	Nor	COMM_FAILURE when running simple Gtk application
135		TBS	407647	nor	Nor	[blocked] Indicate the tree level of items in the Gaim (post 2.0 beta 3.1) buddy list
136		TBS	355524	nor	Nor	[blocked] Flatreview doesn't work in gnome-about panel.
137		TBS	362627	nor	Nor	[blocked] Thunderbird folder properties: no relationship between page tabs and page contents
138		TBS	354433	enh	Low	Add feature to notify user when a new version is available
139		TBS	353446	nor	Nor	[blocked] Orca not correctly reporting key values in gconf-editor
140	Willie	TBS	349394	enh	Nor	Speech Dispatcher Backend
999			381455	nor	Nor	[blocked] Thunderbird does not present labels around dialog text entries
999		TBS	419142	nor	Nor	[blocked] The accessible name for Evolution mail message header list "checkbox" table cells is not useful
999		TBS	419138	nor	Nor	[blocked] In planner, toggle button on end of "Ribbon" doesn't have accessible name/description
999		TBS	415812	nor	Nor	[blocked] Orca sometimes provides incorrect information regarding table headers
999		TBS	434594	min	Nor	status of controls not shown by orca in flat review mode
999		TBS	419137	nor	Nor	[blocked] planner Edit Task Properties dialog has broken accessible component hierarchy
999		TBS	423440	enh	Nor	Permit reloading of scripts while Orca is running
999	Willie	TBS	415201	nor	Nor	Mouse cusor will not change its shape in magnified screen.
999	Willie	TBS	419123	nor	Nor	Modified speech settings do not change immediately in preferences dialog
999	Willie	TBS	412661	enh	Nor	Gecko.py: determine isUselessObject vs. isLayoutOnly relationship
999		TBS	418287	nor	Nor	[blocked] Treat words separated by non-breaking spaces as a single word in OOo
999		TBS	419135	nor	Nor	[blocked] Tables with column headers have accessibility issues
999		TBS	427876	nor	Nor	Orca hangs in linphone and ekiga soft phone
999			420540	enh	Nor	Firefox keyboard control wish list.
999		TBS	431418	tri	Low	Orca abruptly terminates if it wants to open debug.out in a directory that it doesn't have write permission for.
999	Rich	TBS	412359	enh	Nor	Better integration with bug buddy.
999		TBS	434564	enh	Nor	A wish for flat review to be able to move in smallish increments
999		TBS	433951	nor	Nor	Making changes in the Orca Preferences dialog resets the caretContext in Firefox
999		TBS	434780	nor	Nor	[blocked] Orca does not provide access to text attributes in Firefox
999		TBS	431531	enh	Nor	Add support for user-configurable character naming
999		TBS	432308	nor	Nor	[blocked] Problem with Evolution and threads always speaking "expanded 0 items".
999		TBS	432432	nor	Nor	[blocked] Activate action fails on multi-line entries in Firefox
999		TBS	432674	nor	Nor	[pending] In password entries, Orca should respect key echo settings and say "star" for the inserted characters
999		TBS	433802	nor	Nor	Orca prints warnings when Firefox starts
999		TBS	433655	enh	Nor	Orca's structural navigation should wrap at the end of a page
999		TBS	433401	nor	Nor	"Frozen" cells seems to interfere with setting dynamic headers in Calc
999		TBS	419136	nor	Nor	[blocked] Planner toggle button in main window not accessible
999		TBS	434654	nor	Nor	Orca skips a line in flat review mode or with braille navigation (braille up / down).
999		TBS	434600	nor	Nor	cursor routing problem in gedit
999		TBS	433398	nor	Nor	Orca does not provide access to the state of checked menu items in OOo
999		TBS	433323	nor	Nor	Orca does not show the tabs list in Firefox 3.